PAGE  

	AFRICAN UNION
	
	UNION AFRICAINE

	
[image: image1.png]SAAY A




	
	UNIÃO AFRICANA


www.au.int/maritime
Annex C: Plan of Action for Operationalization
[image: image2.png]



2 0 5 0 

A F R I C A’ S 

I N T E G R A T E D 

MARITIME STRATEGY

(2050 AIM STRATEGY®)*

“Together, let’s navigate the future… now! Keep an eye on www.au.int/maritime, and swim with us on Twitter and Facebook in Arabic, English, French, Portuguese and… Kiswahili. Fair winds!”

(End of year email sent on 16 Dec. 2011, by H.E. Mr. Erastus Mwencha, Deputy Chairperson of the AUC to all Staff in Addis and around the world, all Member States and Partners.)

INTRODUCTION.
This 2050 Africa’s Integrated Maritime Strategy (2050 AIM Strategy) Plan of Action for Operationalization was adopted at the African Union (AU) Commission Headquarters in Addis Ababa, Ethiopia, on 06 December 2012 by the 2nd Conference of African Ministers in Charge of Maritime Related Affairs* organized by the African Union back-to-back with the 5th African maritime cross-sectoral Experts Workshop, held on 03-04 December 2012, and the High Level African maritime cross-sectoral Senior Officials meeting which took place on 05 December 2012. 

This Plan of Action constitutes a road map primarily aimed at outlining the global objectives pursued in the bid to improve Africa’s blue economy, the major activities or actions identified for attaining the objectives, the measures of output, the lead and other institutions responsible for the implementation of the activities detailed in the Action Plan. The objectives cover projections for new institutions and structures, wealth creation and human resource development, as well as capacity building for maritime governance. Some of the Action items have been implemented (or are under implementation) by the responsible parties. The Plan of Action will be reviewed and updated every three years. 
At present, the financial implications of the Plan of Action cannot be accurately estimated. However, such estimates will be carried out prior to implementation of each of the activities programmed and reviewed as necessary. 
The AU Commission will remain the main coordination organ for facilitating implementation of the Plan of Action.

“We express our unconditional support to this extremely important initiative and assure the Commission of our full cooperation. We further request all stakeholders to support this particular project which will boost global security standards and benefit future generations of African citizens”. (Ministers and Heads of delegations who attended the 1st Conference of African Ministers in Charge of Maritime Related Affairs, Addis Ababa-Ethiopia, 21 April 2012).
* Ministers, members of the Government/Cabinet, from all AU Member States, dealing with any of the various sectors related to the African Maritime Domain, to include amongst others: Energy, economy, water, water resources, justice/legal, planning and development, tourism, defense, safety, security, social affairs, counter narcotics, fisheries, shipping, ports, harbours and marine infrastructure, trade, labour, marine environment, climate change, oil, gas and mining industry, scientific research, science and Technology. 
	SHORT TERM
(2013 - 2018)

	Programs
	Objectives 
	Actions 
	Lead
	Support partners 
	Measures of output 
	Time frame

	A.S. AIM2050 Strategy Management  
	1. Preparation of AIM Strategy 


	Develop AIMS Strategy
	AU
	Member States
	AU approved AIM Strategy 
	2013

	
	
	Present & create stakeholder awareness of approved AIM Strategy
	AU
	Member States, RECs, RMs, stakeholder, specialised institutions  
	Establish stakeholder buys-in (continental, regional & Sub regional)
	2013

	
	
	Present & create stakeholder awareness of approved AIM Strategy
	AU
	Member States, RECs, RMs, stakeholder, specialised institutions , Strategic Partners
	Inaugural African Maritime Security and Development Conference hosted
	2015

	
	
	Establish specialised management structures 
	AU
	Appointed Committees
	Structures established 
	2013

	
	2. Achieve synergy by Member States 


	Encourage the formulation of regional/national maritime strategy
	Member States, RECs, RMs, stakeholder, specialised institutions  
	
	Regional/National Maritime Strategy
	2018

	
	
	Mobilise implementation resources
	AU, Member States, stakeholders
	Donors, industry etc. 
	Funded programs 
	Ongoing

	
	3. Implementation of short terms phase Business Plan
	Develop Business Plan
	AU (appointed Committee)
	Member States, RECs, RMs, stakeholder, specialised institutions  
	Approved Business Plan
	2013

	
	
	Implement Short Term Business plan 
	All
	AU
	Business Plan Targets and Output achieved
	2018

	
	
	Monitor progress on implementation of AIM programmes  
	AU
	Appropriate Committees
	Annual Monitoring Report
	Annually 

	
	
	Conduct evaluation & impact assessment of Business Plan
	AU
	Appropriate Committees
	Short Term Evaluation & Impact Assessment Report
	2018

	B.S. Maritime Governance Development Programme
	1. Ensure security and safety of maritime transport systems
	Conduct an analysis of the current state of maritime governance across member states
	AU,  Appropriate Technical Committees
	Member States,

Regional Institutions
	Better understanding of the challenges and opportunities for African Maritime Governance
	2018

	
	
	Strengthen Flag state implementation and Port State Control (including accession to Abuja, Indian Ocean and Mediterranean MoUs) and the Djibouti code of conduct
	AU, Member States
	IMO, RECs, RMs and Regional Maritime Institutions
	Improved FSI and PSC.
	2018

	
	
	Provide support for member states for the adoption and ratification of International Maritime treaties
	AU, Member States
	IMO, RECs, RMs and Regional Maritime Institutions
	Increased number of compliant member states 
	2018

	
	
	Promote and encourage the implementation of the African Maritime Transport Charter, 
	AU, Member States
	IMO, RECs, RMs and Regional Maritime Institutions
	AMTC implemented
	2013

	
	
	Promote cooperation with non-AU States, regions and blocks  on information sharing and prosecution of illegal acts against ships 
	AU, Member States
	Regional Maritime institutions and blocks
	Agreement on cooperation established
	2018

	
	
	Conduct research on the establishment of a CEMZA
	AU
	RECs, RMs, Member States
	CEMZA Research report
	2018

	
	
	Conduct an assessment of current MDA (Including needs for Maritime Operation Centres) capabilities 
	AU
	RECs, RMs, Member States
	MDA Status Report 
	2015

	
	
	Develop a Maritime Security Strategy  for Africa
	AU
	Member States
	An AU approved 2050 Maritime Security strategy and implementation plan
	2018

	
	
	Promotion of the adoption and implementation of international treaties
	Member States
	AU, Regional, specialised institutions 
	Compliance with international treaties
	2018

	
	
	i) Promote capacity development for protection of marine environment

ii) establishment of Port facilities (MARPOL)
	Member States
	AU, Regional,  specialised institutions
	Compliance with international treaties
	i) 2018

ii) 2018

	
	6. Provide support for peace and humanitarian operation
	Provide expertise for establishment of Maritime Component to support Africa Standby Force
	AU
	RECs, RMs, UN
	Stable environment 
	2018

	
	7. Outreach initiatives
	Pan African “no more Sea Blindness’” Provide support to eliminate disease 
	AU
	RECs, RMs, Member State, Partners
	A detailed programme and campaign Launched  
	2015

	
	
	Establish an African Maritime Day
	AU
	RECs, RMs, Member State, Partners
	 African Maritime Day event held
	Annual

	C.S. 

Wealth Creation Programme
	1. Enhance wealth creation, and regional and international trade performance through maritime centric capacity and capability 
	Promote and improve the level of ship ownership and  registration by African countries
	AU, RECs RMs and Member states
	FDIs, AfDB, World Bank and strategic partners
	Assess current levels of vessel ownership by Africans

Develop an African Vessel ownership and registration  Plan 


	2013

2018

	
	2. Improve and facilitate intra-Africa maritime trade
	i) Develop and implement framework for promoting intra Africa trade

ii) assessment bottlenecks on transit of goods of landly connected States
	AU, RECs, RMs,
	UNCTAD, AU Partners, AfDB, World Bank
	 Framework Implemented 

Assessment Report developed 
	i) 2018

ii) 2014

	
	3. Promote growth of marine tourism and leisure industry 
	Review Abuja Declaration on sustainable fisheries and aquaculture in Africa , 2005 
	AU, RFM
	FAO
	Domestication of the Declaration 
	2014



	
	
	
	AU, RFM
	FAO
	Established fishery protection zones and monitoring mechanisms in AMD
	2015

	
	
	
	AU, RFM
	FAO, AfDB, World Bank
	A framework for the establishment of 5 Giant African Aquariums
	2015

	
	
	Assess the current capacity and set targets 
	AU, DMA
	Member States
	Assessment Report developed
 
	2015

	
	
	Develop an Maritime Tourism and Leisure for Africa strategic plan 
	AU
	Recognised Tourism Institutions, Member States, Tour Operators, RECs. RMs, AfDB, World Bank
	AU Approved Maritime Tourism and Leisure 


	2014



	
	
	Establish a fully funded Maritime Infrastructure Development Plan in alignment with current African, Regional and National  Infrastructure Development Plans
	AU
	Member States, DFIs, RECs, RMs, AfDB, World Bank 
	Approved Fully Funded Maritime Infrastructure plan 
	2014

	D.S. 

Research and Human resource development 
	1. Improve Africa’s maritime workforce capability 
	i) Conduct study on Africa’s maritime workforce and capacity development 

ii) Develop maritime capacity development programme 
	AU, AU Committees 
	Member States, ECs, RMs, Regional Maritime institutions 
	i) Study developed 
ii) Strategy Approved
ii) programmes developed 
	2015

2018

2018

	
	2. Improve gender balance in maritime sector and development of maritime education and capacity 
	Assess number of women maritime workforce and identify opportunities for increased participation and integration 

ii) strengthening capacity and cooperation of existing Centres of Excellence and establish new CoEs for mariner’s training 

iii) source of fellowships for maritime capacity development capacity 


	i) AU

ii) AU, RECs, RMs,
iii) AU
	i) REMs, RM, AU Partners

ii) IMO, AU Partners 

iii) RECs, RMs, AU Partners
	i) Increased women integration

ii) strong maritime education and development capacity

iii) improved skill capacity 


	2015

	
	3. Improve maritime research capacity
	i) Assess current capabilities for maritime research activities 

ii) Implementation of capacity building programmes on maritime research 
	i) AU

ii) AU, 
	I) Research institutes, IOC, RECs, RMs, UNESCO etc.

II) Research institutes, IOC, RECs, RMs, UNESCO etc. 
	i) Identification of gaps, requirement and area of focus

ii) Approved Maritime Research Programme  
	2014

2014

	Cadetship programme
	4. increase number of Africans seafarers 
	Securing of onboard training 
	AU, Member States, 
	Donors, AU Partners 
	Develop a database of African Seafarers

African Maritime Cadetship Programme established 
	2013

2013


	MEDIUM TERM
(2019 - 2030)

	Programs 
	Objectives 
	Actions 
	Lead 
	Support partners 
	Measures of output 
	Time frame

	A.M. AIM2050 Strategy Management  
	1. Achieve synergy by Member States
	Implement the regional/national maritime strategy
	Member States, RECs, RMs, stakeholder, specialised institutions  
	AU
	Objectives achieved
	2030

	
	
	Present & create stakeholder awareness of approved AIM Strategy
	AU
	Member States, RECs, RMs, stakeholder, specialised institutions , Strategic Partners
	Host an African Maritime Security and Development Conference
	2019

	
	2. Implementation of medium term Plan
	Review Approved  Business Plan
	AU (appointed Committee)
	Member States, RECs, RMs, stakeholder, specialised institutions  
	Approved Business Plan reviewed and updated
	2018

	
	
	Implement Medium Term Objectives in approved Business Plan 
	All
	AU
	Medium Term objectives achieved
	2030

	
	
	Monitor progress on implementation in the medium term  
	AU
	Appropriate Committees
	Annual Monitoring Report
	Annually 

	
	
	Conduct medium term plan evaluation & impact assessment of Business Plan
	AU
	Appropriate Committees
	Medium Term Evaluation & Impact Assessment Report
	2030

	B.M. Maritime Governance Development Programme
	1. Ensure security and safety of maritime transport system
	Implement the African Maritime Governance plan (Based on the analysis conducted)
	AU, Member States
	IMO, EU, UN, RECs, RMs, Specialised and International Institutions
	Recommendations of the analysis implemented
	2030

	
	
	Implement the Port State MOUs and adopted International Treaties
	Member States, RECs, RMs
	AU, IMO, UN, EU 
	States in compliance with MOUs and International Treaties
	2030

	
	
	 Implement CEMZA Legal regimes and institutional arrangement
	Member States, RECs, RMs
	AU
	CEMZA established
	2030

	
	
	Implement recommendations of the MDA report (Including needs for Maritime Operation Centres) capabilities 
	Member States, RECs, RMs
	AU
	MDA recommendations implemented  
	2018

	
	
	Implement a the approved maritime Security Strategy  for Africa
	AU
	Member States, RECs, RMs, Strategic Partners
	Maritime Security Strategy Implementation plan objectives achieved  
	2030


	MEDIUM TERM
(2019 - 2030)

	Programs 
	Objectives 
	Actions 
	Lead 
	Support partners 
	Measures of output 
	Time frame

	C.M. 

Wealth Creation Programme
	1. Enhance wealth creation, and regional and international trade performance through maritime centric capacity and capability 
	Establish framework and targets for developing Africa’s shipbuilding, port and maintenance capacity 
	AU, Port Association, Member States
	Strategic Partners,  RECs, RMs,, DFIs, AfDB, World Bank
	Framework developed 
	2020

	
	
	Promote and improve the level of ship ownership and  registration by African countries
	RECs RMs and Member states
	AU, FDIs, AfDB, World Bank and strategic partners
	Attainment of at least 10% of global cargo carrying capacity by African owned shipping
	2030

	
	
	Address all bottlenecks on transit of goods of landly connected States
	RECs RMs and Member states
	AU,
	An increase from 10% to 50% Intra Africa Trade
	2030

	
	
	Establish 2  Giant Aquariums  by 2050
	AU
	International conservation organisations, Member States, AfDB, World Bank
	At least 2  Giant Africa Aquariums established 
	2030

	
	
	Implement the Africa Maritime Tourism and Leisure strategic plan
	AU
	Recognised Tourism Institutions, Member States, Tour Operators, RECs. RMs, AfDB, World Bank 
	At least 15% contribution to GDP by Maritime tourism and leisure
	2030

	
	
	Implement the Approved Maritime Infrastructure Development Plan
	
	
	Phased Ship and Boat Building and Repair plan targets achieved

Phased Port Infrastructure plan targets achieved 

Maritime Facilities Plan implemented 
	2020




	MEDIUM TERM
(2019 - 2030)

	Programs 
	Objectives
	Actions
	Lead
	
	
	Program 

	D.M. 

Research and Human resource development 
	1. Improve Africa’s maritime workforce and research capability 
	Implement the approved
African maritime Human Resource Development (Incorporating the integration of Women as a strategic group)
	AU, AU Committees 
	Member States, RECs, RMs, Regional Maritime institutions 
	Phased Implementation of the Maritime Human Resource Strategy and Plan 
100% of identified targets achieved
	Ongoing

2030

	
	
	Strengthening capacity and cooperation of existing Centres of Excellence and establish new CoEs for mariner’s training 
	i) AU


	i) REMs, RM, AU Partners


	Africa has fully capacitated World class Maritime Centre of Excellence per region (RECs)

	2030

	
	2. Increase the number of African Seafarers 
	Promote the development of the African Seafarer and Implement the African Cadetship Programme
	AU 
	REMs, RM, AU, Member States Partners, IMO, 
	At least 10% of World Seafarers  are Africans
	2020

	
	3. Improve maritime research capability
	Implement the AIMS Maritime Research Programme
	Academic,  Research Institutions,
	RECs, RMs ,AU, IMO, UNESCO, etc
	Maritime Research programme outputs achieved   
	2030


	LONG TERM
(2031 - 2050)

	Programs 
	Objectives 
	Actions 
	Lead 
	Support partners 
	Measures of output 
	Time frame

	A.L. AIM2050 Strategy Management  
	1.Regional Maritime Strategy  synergy
	Work coherently to synergize regional/national maritime strategy
	Member States, RECs, RMs, stakeholder, specialised institutions  
	AU
	Objectives achieved
	2050

	
	
	create stakeholder awareness of need of national/regional maritime Strategy synergy
	AU
	Member States, RECs, RMs, stakeholder, specialised institutions , Strategic Partners
	Regular African Maritime Stakeholder Conference
	2031

	
	2. Review medium term Plan
	Evaluate the entire process, challenges and achievements and craft a revised Strategy for 2051 onwards
	AU and Member States
	Member States, RECs, RMs, stakeholder, specialised institutions  
	Revised Strategy Plan reviewed, updated and approved
	2045

	C.L. 

Wealth Creation Programme
	1. Enhance wealth creation, and regional and international trade performance through maritime centric capacity and capability 
	Implement framework established in the Medium for developing Africa’s shipbuilding, port and maintenance capacity 
	AU, Port Association, Member States
	Strategic Partners, AfDB, World Bank, RECs, RMs,, DFIs
	Ships being building and maintenance on the African continent achieved 
	2050

	
	
	Ship ownership and  registration by African countries increases 
	RECs RMs and Member states
	AU, FDIs, AfDB, World Bank and strategic partners
	Attainment of at least 15% of global cargo carrying capacity by African owned shipping
	2050

	
	
	Easy flow of Transit of goods of landly connected States 
	Member  States, RECs, RMs
	AU,
	Increased of Intra Africa Trade by 30%
	2050

	
	
	Establish 3  Giant Aquariums  
	AU
	Member  States, RECs, RMs, AfDB, World Bank
	5   Giant Aquariums built   
	2050

	
	
	Africa Maritime Tourism and Leisure increases
	Member States
	AU, AfDB, World Bank, Partners
	Increased Africa participation in Tourism and leisure by 30% as percentage of GDP
	2050

	
	
	Maritime Infrastructure Development Established
	Member States
	AU, AfDB, World Bank Partners
	Shipping & Port infrastructure competitive relative to the rest of the world
	2050

	
	
	Implement the Exploration and Exploitation of maritime resources Plan
	Member States
	AU, AfDB, World Bank, Partners
	Increased Africa’s participation in exploration and exploitation of its marine resources. 
	2050


Annex C: 2050 AIM Strategy PoA. Last update: 11/12/2012 15:23 







1

_1413349946

