## Consultancy
AFRICAN UNION ANNUAL PROCUREMENT PLAN AS OF AUGUST 2025
CONSULTANCY SERVICES
| S/N | Description | Reference Number | Category Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
| 1 | Communications and stakeholder relations (CSR) guideline(s) Acquisition of a public sector audit capacity-building firm (e.g. AFROSAI-E) to provide consultancy on OIO's Communication and Stakeholder Relations (CSR) Guidelines. | AUC/OIO/CS/001 | CS | CDS | LC | 14718 | MS(100%) | 2025-06-06 | 2025-06-11 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 2 | External Quality Assessment (EQA)(Consultancy Services) | AUC/OIO/CS/002 | CS | CQS | LC | 70600 | JFA(Bucket Fund) (21%) IPs(79%) | 2025-01-30 | 2025-02-04 | 2025-02-25 | 2025-03-18 | 2025-03-25 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27
| 3 | Recruitment of five (5) individual consultants to draft the African Union Economic Flagship Report "Africa's Development Dynamics" | AUC/ETTIM/CS/001 | CS | QCBS | OC | 75000 | MS(100%) | 2025-02-03 | 2025-02-08 | 2025-03-01 | 2025-03-22 | 2025-03-29 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01
| 4 | Recruitment of ten juniour consultants to support implementation of the tax and illicit financial flows strategy | AUC/ETTIM/CS/002 | CS | QCBS | OC | 50000 | EU(100%) | 2025-03-12 | 2025-03-17 | 2025-04-01 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03
| 5 | Consultancy Services to evaluate the implementation of African Digital Financial Inclusion Strategy | AUC/ETTIM/CS/003 | CS | INDV | LC | 22000 | EU(100%) | 2025-04-07 | 2025-04-12 | 2025-05-03 | 2025-05-24 | 2025-05-31 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03
| 6 | Consultancy Services to undertake a study on the implementation of the African Union Financial Institutions | AUC/ETTIM/CS/004 | CS | INDV | OC | 36000 | MS(100%) | 2025-04-25 | 2025-04-30 | 2025-05-21 | 2025-06-11 | 2025-06-18 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21
| 7 | Consultancy service to support the implementation of economic policies and strategies to foster high and sustained rates of inclusive economic growth and structural economic transformation | AUC/ETTIM/CS/005 | CS | INDV | OC | 24000 | MS(100%) | 2025-05-15 | 2025-05-20 | 2025-06-10 | 2025-07-01 | 2025-07-08 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10
| 8 | Consultqncy Service to undertake analysis on strengtening Domestic Resource Mobilisation (DRM) productive transformation | AUC/ETTIM/CS/006 | CS | INDV | OC | 24000 | MS(100%) | 2025-05-15 | 2025-05-20 | 2025-06-10 | 2025-07-01 | 2025-07-08 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10
| 9 | Recruitment of Consultant-Raise Awareness on the Value of Intellectual Property Rights for SMEs, Start-Ups, Innovation & Industralization | AUC/ETTIM/CS/007 | CS | INDV | LC | 50000 | MS(100%) | 2025-05-15 | 2025-05-20 | 2025-06-10 | 2025-07-01 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13
| 10 | Consultancy Services to Develop African Tourism Certification and Accreditation scheme | AUC/ETTIM/CS/008 | CS | INDV | OC | 108000 | MS(100%) | 2025-01-15 | 2025-01-20 | 2025-02-04 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08
| 11 | Consultancy Services to develop a Destination Management System and AU Tourism Portal | AUC/ETTIM/CS/009 | CS | INDV | OC | 120000 | MS(100%) | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 12 | Consultancy Services to develop and establish an integrated tourism system | AUC/ETTIM/CS/010 | CS | INDV | OC | 120000 | MS(100%) | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 13 | Consultancy Services to Support the Africa Industrialization Week | AUC/ETTIM/CS/011 | CS | INDV | OC | 30000 | EU(100%) | 2025-08-15 | 2025-08-20 | 2025-09-10 | 2025-10-01 | 2025-10-08 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10
| 14 | Consultancy Services to Support the African Women In Processing Summit During the Africa Industrialization Week | AUC/ETTIM/CS/012 | CS | INDV | OC | 14400 | MS and EU(100%) | 2025-08-15 | 2025-08-20 | 2025-09-10 | 2025-10-01 | 2025-10-08 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10
| 15 | Consultancy service to Monitor Progress on the implementation of AIDA | AUC/ETTIM/CS/013 | CS | INDV | OC | 72000 | MS and EU (100%) | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 16 | Consultancy Services to Support countries to implement the 5-10% allocation of their national budgets towards industrialization | AUC/ETTIM/CS/014 | CS | INDV | OC | 6000 | EU(100%) | 2025-06-18 | 2025-06-23 | 2025-07-14 | 2025-08-04 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13
| 17 | Consultancy Services to Support countries to domesticate and implement the African Union Fashion Development Strategy | AUC/ETTIM/CS/015 | CS | INDV | OC | 32400 | EU(100%) | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 18 | Consultancy Services to Support SEZ | AUC/ETTIM/CS/016 | CS | INDV | OC | 5400 | MS and EU(100%) | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 19 | Consultancy service to undertake studies on best practices on SEZ development in Africa | AUC/ETTIM/CS/017 | CS | INDV | OC | 60000 | MS and EU (100%) | 2025-07-25 | 2025-07-30 | 2025-08-20 | 2025-09-10 | 2025-09-17 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20
| 20 | Consultancy Services to Popularize the AU Model Law on SEZs in AU MS and RECsn | AUC/ETTIM/CS/018 | CS | INDV | OC | 24000 | MS and EU(100%) | 2025-06-25 | 2025-06-30 | 2025-07-21 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20
| 21 | Consultancy Services tp conduct feasibility studies on viable and innovative SEZs | AUC/ETTIM/CS/019 | CS | INDV | OC | 60000 | EU(100%) | 2025-06-01 | 2025-06-06 | 2025-06-27 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27
| 22 | Consultancy Services to conduct continental Manufacturing Survey | AUC/ETTIM/CS/020 | CS | INDV | OC | 60000 | MS and EU(100%) | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 23 | Consultancy Services to undertake research on Manufacturing | AUC/ETTIM/CS/021 | CS | INDV | OC | 84000 | MS and EU(100%) | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 24 | Consultancy service to Support African women in Processing with trainings in various areas to improve their businesses | AUC/ETTIM/CS/022 | CS | INDV | OC | 60000 | MS and EU (100%) | 2025-08-25 | 2025-08-30 | 2025-09-20 | 2025-10-11 | 2025-10-18 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20
| 25 | Consultancy Services to support African women in Processing to financing opportunities | AUC/ETTIM/CS/023 | CS | INDV | OC | 9000 | MS and EU(100%) | 2025-06-25 | 2025-06-30 | 2025-07-21 | 2025-08-11 | 2025-08-18 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20
| 26 | Consultancy Services to support African countries and RECs to domesticate the AU Commodity Strategy | AUC/ETTIM/CS/024 | CS | INDV | OC | 50000 | MS & EU(100%) | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 27 | Consultancy Services to Finalize the Drafting and Validation of the African Union Model Law on Mineral Resources | AUC/ETTIM/CS/025 | CS | INDV | OC | 48600 | MS and EU(100%) | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 28 | Consultancy Services to to support Deep Seabed Mining (DSM) Through R&D in Support for Sustainable Blue Economy | AUC/ETTIM/CS/026 | CS | INDV | OC | 45000 | MS and EU(100%) | 2025-09-15 | 2025-09-20 | 2025-10-11 | 2025-11-01 | 2025-11-08 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11
| 29 | Consultancy service to Support the Commodity focused industrialization | AUC/ETTIM/CS/027 | CS | INDV | OC | 12000 | MS & EU (100%) | 2025-05-18 | 2025-05-23 | 2025-06-13 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13
| 30 | Consultancy Services to support the Continental Networks of Commodity Producers in Mining, Agriculture and Energy | AUC/ETTIM/CS/028 | CS | INDV | OC | 28800 | MS and EU(100%) | 2025-05-20 | 2025-05-25 | 2025-06-15 | 2025-07-06 | 2025-07-13 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15
| 31 | Consultancy Services to develop a Continental Oil and Gas Program for Africa | AUC/ETTIM/CS/029 | CS | INDV | OC | 48000 | MS and EU(100%) | 2025-05-18 | 2025-05-23 | 2025-06-13 | 2025-07-04 | 2025-07-11 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13
| 32 | Consultancy Services to Develop and implement the Oil and Gas programme | AUC/ETTIM/CS/030 | CS | INDV | OC | 24000 | MS and EU(100%) | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 33 | Consultancy Services to to support the implementation of the AQP and MiA | AUC/ETTIM/CS/031 | CS | INDV | OC | 18000 | MS, GIZ and EU(100%) | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
| 34 | Consultancy service to develop new standards for commonly traded products | AUC/ETTIM/CS/032 | CS | INDV | OC | 21600 | MS, GIZ and EU(100%) | 2025-06-01 | 2025-06-06 | 2025-06-27 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27
| 35 | Consultancy Services to Raise awareness on the value of Intellectual Property Rights for SMEs, Start-ups, Innovation and Industrialization. | AUC/ETTIM/CS/033 | CS | INDV | OC | 48800 | MS and EU(100%) | 2025-06-01 | 2025-06-06 | 2025-06-27 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27
| 36 | Consultancy Services to develop and update Investment Promotion Network (AIPN) website | AUC/ETTIM/CS/034 | CS | INDV | OC | 13500 | MS and Turk(100%) | 2025-08-01 | 2025-08-06 | 2025-08-27 | 2025-09-17 | 2025-09-24 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
| 37 | Consultancy Services to Support African Youth Startups to market their innovations | AUC/ETTIM/CS/035 | CS | INDV | OC | 18240 | MS and EU(100%) | 2025-07-01 | 2025-07-06 | 2025-07-27 | 2025-08-17 | 2025-08-24 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26
| 38 | Consultancy Services to support the AU SME FORUM | AUC/ETTIM/CS/036 | CS | INDV | OC | 9300 | MS and EU(100%) | 2025-05-30 | 2025-06-04 | 2025-06-25 | 2025-07-16 | 2025-07-23 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25
| 39 | Mineral Policy development Consultant-African Minerals Development Center (AMDC) | AUC/ETTIM/CS/037 | CS | QBS | OC | 15000 | OSI | 2025-08-08 | 2025-08-13 | 2023-08-29 | 2025-09-05 | 2025-09-12 |  |  |  | 2025-08-19 | 2025-08-26
| 40 | Communications Consultant-African Minerals Development Center (AMDC) | AUC/ETTIM/CS/038 | CS | QBS | OC | 15000 | OSI | 2025-08-08 | 2025-08-13 | 2023-08-29 | 2025-09-05 | 2025-09-12 |  |  |  | 2025-08-19 | 2025-08-26
| 41 | Junior Expert On The African trade Observatory, Minerals & Tourism-African Minerals Development Center (AMDC) | AUC/ETTIM/CS/039 | CS | QBS | OC | 15000 | OSI | 2025-08-08 | 2025-08-13 | 2023-08-29 | 2025-09-05 | 2025-09-12 |  |  |  | 2025-08-19 | 2025-08-26
| 42 | Recruitment of consultants for the World Bank Food Resilence Support Project Implementation Unit: (1) Project coordinator (2) Climate smart agriculture specialist (3) Trade Specialist (4) Policy specialist (5) Knowledge management and communication officer (6) Monitoring and evaluation officer (7) Finance officer, (8) Project assistant (9) Procurement officer. | AUC/ARD/CS/001 | CS | INDV | OC | 2850000 | MS(100%) | 2025-01-05 | 2025-01-10 | 2025-01-31 | 2025-02-21 | 2025-02-28 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02
| 43 | Recruit consultant to establish and operationalize Regional Rapid Alert System for Food and Feed | AUC/ARD/CS/002 | CS | QCBS | OC | 450100 | AfDB(100%) | 2025-01-12 | 2025-01-17 | 2025-02-16 | 2025-03-09 | 2025-03-16 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18
| 44 | Recruit consultant to facilitate the development of national guidelines on biofortification, the registration, certification and production of biofortified seeds | AUC/ARD/CS/003 | CS | QCBS | OC | 128600 | AfDB(100%) | 2025-01-12 | 2025-01-17 | 2025-02-16 | 2025-03-09 | 2025-03-16 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18
| 45 | Recruit consultant to facilitate partnerships to develop, document and disseminate nutrition-sensitive technologies to smallholder farmers | AUC/ARD/CS/004 | CS | QCBS | OC | 128600 | AfDB(100%) | 2025-06-30 | 2025-07-05 | 2025-08-04 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04
| 46 | Recruit consultant to conduct Training of trainers for smallholder farmers and SMEs APEX bodies | AUC/ARD/CS/005 | CS | QCBS | OC | 192900 | AfDB(100%) | 2025-06-30 | 2025-07-05 | 2025-08-04 | 2025-08-25 | 2025-09-01 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04
| 47 | Recruit consultant to facilitate the development of national guidelines on biofortification, the registration, certification and production of biofortified seeds or cuttings | AUC/ARD/CS/006 | CS | QCBS | OC | 128600 | AfDB(100%) | 2025-07-30 | 2025-08-04 | 2025-09-03 | 2025-09-24 | 2025-10-01 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03
| 48 | Recruit consultant to facilitate twinning and peer learning for laboratories | AUC/ARD/CS/007 | CS | QCBS | OC | 192900 | AfDB(100%) | 2025-05-30 | 2025-06-04 | 2025-07-04 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03
| 49 | Recruit consultant to conduct Training of laboratory personnel to enhance their skills on analytical testing and sampling of food safety hazards in priority regional food commodities | AUC/ARD/CS/008 | CS | QCBS | OC | 128600 | AfDB(100%) | 2025-05-30 | 2025-06-04 | 2025-07-04 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03
| 50 | Recruit consultant to support the development, and implementation of internationally recognized laboratory management system such as ISO/IEC 17025annual audit | AUC/ARD/CS/009 | CS | QCBS | OC | 192900 | AfDB(100%) | 2025-05-30 | 2025-06-04 | 2025-07-04 | 2025-07-25 | 2025-08-01 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03
| 51 | Recruit consultant to Conduct Annual audit | AUC/ARD/CS/010 | CS | LCS | LC | 30211 | AfDB(100%) | 2025-09-30 | 2025-10-05 | 2025-11-04 | 2025-11-25 | 2025-12-02 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04
| 52 | Recruit consultant to conduct Mid-term review and prepare completion report | AUC/ARD/CS/011 | CS | INDV | LC | 22659 | AfDB(100%) | 2025-09-30 | 2025-10-05 | 2025-11-04 | 2025-11-25 | 2025-12-02 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04
| 53 | Recruit consultant to conduct training laboratory personnel to enhance their skills on analytical testing and sampling of food safety hazards in priority regional food commodities | AUC/ARD/CS/012 | CS | INDV | OC | 257200 | AfDB(100%) | 2025-07-30 | 2025-08-04 | 2025-09-03 | 2025-09-24 | 2025-10-01 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03
| 54 | Recruit consultant to support selected MSMEs (including WSMEs) to install HACCP or achieve product certification through a match funding arrangement | AUC/ARD/CS/013 | CS | INDV | LC | 64300 | AfDB(100%) | 2025-09-30 | 2025-10-05 | 2025-11-04 | 2025-11-25 | 2025-12-02 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04
| 55 | Recruit consultant to conduct Training on laboratory quality assurance systems | AUC/ARD/CS/014 | CS | INDV | LC | 64300 | AfDB(100%) | 2025-10-30 | 2025-11-04 | 2025-12-04 | 2025-12-25 | 2026-01-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03
| 56 | Recruiting Project coordinator for the SFNA project | AUC/ARD/CS/015 | CS | INDV | OC | 135952 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 57 | Recruiting Project accountant for the SFNA project | AUC/ARD/CS/016 | CS | INDV | OC | 135952 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 58 | Recruiting a Food Safety Expert (Food Risk Management) for the SFNA project | AUC/ARD/CS/017 | CS | INDV | LC | 67976 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 59 | Recruiting a Nutrition Expert for the SFNA project | AUC/ARD/CS/018 | CS | INDV | LC | 67976 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 60 | Recruiting Procurement Expert for the SFNA project | AUC/ARD/CS/019 | CS | INDV | LC | 67976 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 61 | Procuring Consulting Service of a Food Safety Expert (Laboratories) for the SFNA project | AUC/ARD/CS/020 | CS | INDV | LC | 67976 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 62 | Recruiting Communication Expert for the SFNA project | AUC/ARD/CS/021 | CS | INDV | LC | 67976 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 63 | Recruiting an Administrative Secretary for SFNA project | AUC/ARD/CS/022 | CS | INDV | LC | 36000 | AfDB(100%) | 2025-06-01 | 2025-06-06 | 2025-07-06 | 2025-07-27 | 2025-08-03 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05
| 64 | Consultancy service for procurement for Custodian Bank and Fund Managers | AUC/PFS/CS/001 | CS | QCBS | OC | 2000000 | MS(100%) | 2025-01-01 | 2025-01-06 | 2025-02-05 | 2025-02-26 | 2025-03-05 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07
| 65 | Professional English Content Editor for Peace Fund Magazine | AUC/PFS/CS/002 | CS | DIR | LC | 5000 | MS(100%) | 2025-01-01 | 2025-01-06 | 2025-02-05 | 2025-02-26 | 2025-03-05 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07
| 66 | consultancy service to upgrade / Enhance ERP Legacy System | AUC/ERP/CS/001 | CS | RFB | OC | 1609693 | WB | 2025-04-25 | 2025-04-30 | 2025-05-30 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30
| 67 | consultancy service toSAP Value Realization/ Support | AUC/ERP/CS/002 | CS | RFB | OC | 200000 | WB | 2025-04-25 | 2025-04-30 | 2025-05-30 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30
| 68 | consultancy service for ERP Capacity Building (Managers, Business Users, ERP Team) | AUC/ERP/CS/003 | CS | RFB | OC | 200000 | WB | 2025-04-25 | 2025-04-30 | 2025-05-30 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30
| 69 | Conduct Policy and strategic studies in each of the 4 sectors (EO, Sat-Nav, SatCom, Astronomy-space science) | AUC/ESTI/AfSA/CS/001 | CS | QCBS | OC | 800000 | EU(100%) | 2025-04-15 | 2025-04-20 | 2025-05-20 | 2025-06-10 | 2025-06-17 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20
| 70 | Consultancy trainings for peer-to-peer institutional capacity building programme on space policy and programmatic needs | AUC/ESTI/AfSA/CS/002 | CS | QCBS | LC | 100000 | EU(100%) | 2025-04-30 | 2025-05-05 | 2025-06-04 | 2025-06-25 | 2025-07-02 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04
| 71 | AfSA website development | AUC/ESTI/AfSA/CS/003 | CS | QCBS | OC | 300000 | EU(100%) | 2025-05-01 | 2025-05-06 | 2025-06-05 | 2025-06-26 | 2025-07-03 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05
| 72 | Development, Production and Dissemination of Use Case Materials | AUC/ESTI/AfSA/CS/004 | CS | QCBS | OC | 250000 | EU(100%) | 2025-05-01 | 2025-05-06 | 2025-06-05 | 2025-06-26 | 2025-07-03 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05
| 73 | Development, Production and Dissemination of Policy briefs | AUC/ESTI/AfSA/CS/005 | CS | QCBS | OC | 300000 | EU(100%) | 2025-05-01 | 2025-05-06 | 2025-06-05 | 2025-06-26 | 2025-07-03 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05
| 74 | Consultants to support implementation of various activities and thematics (Technical; Administration; Management, Monitoring and Evaluation; Communication etc.) of the GMES and Africa Programme | AUC/ESTI/AfSA/CS/006 | CS | CQS | LC | 100000 | EU(100%) | 2025-03-30 | 2025-04-04 | 2025-05-04 | 2025-05-25 | 2025-06-01 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04
| 75 | Procurement of Procurement Officer | AUC/ESTI/AfSA/CS/007 | CS | INDV | LC | 42000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 76 | Recruitment of Adminstrative Officer | AUC/ESTI/AfSA/CS/008 | CS | INDV | LC | 60000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 77 | Recruitment of Senior Advisor | AUC/ESTI/AfSA/CS/009 | CS | INDV | LC | 48000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 78 | Recruitment of IT Expert | AUC/ESTI/AfSA/CS/010 | CS | INDV | LC | 42000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 79 | Recruitment of Knowledge Management Expert | AUC/ESTI/AfSA/CS/011 | CS | INDV | LC | 84000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 80 | Recruitment of Legal Officer | AUC/ESTI/AfSA/CS/012 | CS | INDV | LC | 30000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 81 | Recruitment of Technical Planning Expert | AUC/ESTI/AfSA/CS/013 | CS | INDV | LC | 84000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 82 | Recruitment Of Assistant Accountant | AUC/ESTI/AfSA/CS/014 | CS | INDV | LC | 36000 | EU-SPACE | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04
| 83 | Consultancy Servicde to Develop an oline survey on the guidelines for the AUCTA | AUC/ESTI/CS/001 | CS | INDV | OC | 10000 | EU(100%) | 2025-03-03 | 2025-03-08 | 2025-03-23 | 2025-04-13 | 2025-04-20 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-04-27 | 2025-05-04
| 84 | Consultancy Service to develop M&E Tools for the CTQF | AUC/ESTI/CS/002 | CS | INDV | OC | 10000 | EU(100%) | 2025-04-12 | 2025-04-17 | 2025-05-17 | 2025-06-07 | 2025-06-14 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17
| 85 | Consultancy Service to Develop the ATWB and the CoP Platforms for Teachers | AUC/ESTI/CS/003 | CS | INDV | OC | 28000 | EU(100%) | 2025-05-12 | 2025-05-17 | 2025-06-01 | 2025-06-22 | 2025-06-29 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-06 | 2025-07-13
| 86 | Consultancy Service to Promote Digital Skills for Teacher | AUC/ESTI/CS/004 | CS | INDV | OC | 20000 | EU(100%) | 2025-06-12 | 2025-06-17 | 2025-07-17 | 2025-08-07 | 2025-08-14 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16
| 87 | Consultancy for Digitalization of Finance Directorate Registry | AUC/FIN/CS/001 | CS | LCS | OC | 148900 | WB(100%) | 2025-01-20 | 2025-01-25 | 2025-02-24 | 2025-03-17 | 2025-03-24 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26
| 88 | Consultancy to Undertake Implementation of BCM - Bank Reconciliations and Roll it out to other offices | AUC/FIN/CS/002 | CS | QCBS | OC | 249500 | China (100%) | 2025-01-30 | 2025-02-04 | 2025-02-19 | 2025-03-12 | 2025-03-19 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21
| 89 | Consultation to SAP Enhancements and prepare for S/4HANA Conversion | AUC/FIN/CS/003 | CS | QCBS | OC | 232980 | WB (100%) | 2025-04-13 | 2025-04-18 | 2025-05-03 | 2025-05-24 | 2025-05-31 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03
| 90 | Consultancy to Strengthen Internal controls and Business proceses for efficiency and effectiveness | AUC/FIN/CS/004 | CS | LCS | LC | 50000 | WB (100%) | 2025-03-12 | 2025-03-17 | 2025-04-01 | 2025-04-22 | 2025-04-29 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01
| 91 | Consultancy to update AU Budget Manual and Accounting Procedures | AUC/FIN/CS/005 | CS | LCS | OC | 49800 | WB (100%) | 2025-02-12 | 2025-02-17 | 2025-03-04 | 2025-03-25 | 2025-04-01 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04
| 92 | Consultancy to Conduct external audit of Partners Accounts (JFA,NORWAY,WORLDBANK) in Collaboration with PMRM | AUC/FIN/CS/006 | CS | LCS | OC | 120000 | JFA (33%), WB (33%), Norway ( 33%) | 2025-03-12 | 2025-03-17 | 2025-04-01 | 2025-04-22 | 2025-04-29 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01
| 93 | Consultancy to Institutionalise the Multiyear Planning and Budgeting process | AUC/FIN/CS/007 | CS | LCS | OC | 113000 | EU-AUPPAP | 2025-02-22 | 2025-02-27 | 2025-03-14 | 2025-04-04 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14
| 94 | Consultancy to Enhance the IPSAS computer based e-learning platform | AUC/FIN/CS/008 | CS | LCS | LC | 29840 | JFA (100%) | 2025-03-10 | 2025-03-15 | 2025-03-30 | 2025-04-20 | 2025-04-27 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30
| 95 | Consultancy firm to design an integrated KM digital solution and platform (and identify people, and ICT requirements AU wide | AUC/ICD/CS/001 | CS | INDV | OC | 8000 | MS(100%) | 2025-03-14 | 2025-03-19 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18
| 96 | Consultancy service for the engagment of Junior Graphics Designer | AUC/ICD/CS/002 | CS | QCBS | OC | 15000 | MS(100%) | 2025-07-01 | 2025-07-06 | 2025-08-05 | 2025-08-26 | 2025-09-02 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05
| 97 | Consultancy service for Medical Relief | AUC/MHSD/CS/001 | CS | INDV | OC | 449032 | MS | 2025-03-01 | 2025-03-06 | 2025-04-05 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05
| 98 | Consultancy service for Baby Care Centre | AUC/MHSD/CS/002 | CS | INDV | OC | 46160 | MS | 2025-03-01 | 2025-03-06 | 2025-04-05 | 2025-04-26 | 2025-05-03 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05
| 99 | Consultancy service to Develop and implement record management system | AUC/OSSD/CS/001 | CS | QCBS | OC | 50000 | WB | 2025-02-02 | 2025-03-04 | 2025-03-25 | 2025-04-01 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11
| 100 | hire a consultancy firm for Comprehensive Evaluation and Functionality Assessment of the E-Procurement System | AUC/OSSD/CS/002 | CS | QCBS | OC | 70000 | WB | 2025-03-02 | 2025-04-01 | 2025-04-22 | 2025-04-29 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08
| 101 | hire a consultancy firm for Certification of ISO 9001:2015 Qms for SCMD | AUC/OSSD/CS/003 | CS | QCBS | OC | 45000 | WB | 2025-04-10 | 2025-05-10 | 2025-05-31 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17
| 102 | Hire an individual consultant to support regional offices and organs | AUC/OSSD/CS/004 | CS | QCBS | OC | 20000 | MS | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 103 | Hire an individual consultant - procurement monitoring and evaluation | AUC/OSSD/CS/005 | CS | QCBS | OC | 50000 | MS | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 104 | Conduct Annual Asset Verification Exercise | AUC/OSSD/CS/006 | CS | QCBS | LC | 75000 | MS | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 105 | Automation of Fixed Asset Operations | AUC/OSSD/CS/007 | CS | QCBS | LC | 100000 | WB | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 106 | Review Marehouse Management Manual | AUC/OSSD/CS/008 | CS | QCBS | OC | TBA | WB | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 107 | Hiring trainer(s) for in-sector training on Management of Recovered SALW | AUC/PAPS/CMD/CS/001 | CS | INDV/CDS | LCS/DC | 40000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 108 | Hiring trainer(s) for HQ MNJTF P/CVE Training | AUC/PAPS/CMD/CS/002 | CS | INDV/CDS | LCS/DC | 40000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 109 | Hiring trainer(s) for HQ MNJTF and in-sector training Protection of Civilians | AUC/PAPS/CMD/CS/003 | CS | INDV/CDS | LCS/DC | 40000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 110 | Commission a study on Africa's practice's and lessons in implementing the Women, Peace and Security Agenda. | AUC/PAPS/CMD/CS/004 | CS | INDV | OC | 16000 | IP(100%) | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 111 | Develop learning modules, online self-paced courses on Women Peace and Security thematic | AUC/PAPS/CMD/CS/005 | CS | INDV | OC | 10000 | IP(100%) | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 112 | Set up and Operationalize a Continental Knowledge Management Platform on Women, Peace and Security Agenda in Africa | AUC/PAPS/CMD/CS/006 | CS | INDV | LC | 10220 | IP(100%) | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 113 | Provide institutional support for the revitalization of CEWS (updating CEWS frameworks, capacity building, technical assistance etc) | AUC/PAPS/CMD/CS/007 | CS | INDV | LC | 56537.46 | EU APSA IV (100%) | 2025-03-02 | 2025-03-07 | 2025-03-14 | 2025-04-04 | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-04-18 | 2025-04-25
| 114 | Development of a Policy on Gender mainstreaming for AU PSO | AUC/PAPS/CMD/CS/008 | CS | INDV | LC | 11719 | IP(100%) | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 115 | Support women participation in conflict prevention, early warning, conflict management, post conflict reconstruction and in political transitional processes). | AUC/PAPS/CMD/CS/009 | CS | QCBS | LC | 40375 | JFA | 2025-05-15 | 2025-05-20 | 2025-06-03 | 2025-06-07 | 2025-06-20 | 2025-06-25 | 025-06-2025 | 2025-06-15 | 2025-06-20 | 2025-06-25
| 116 | Organize income-generating capacity development initiatives as a sustainable canvass for addressing deterrents of peace and stability in West Africa | AUC/PAPS/CMD/CS/010 | CS | QCBS | LC | 28375 | JFA | 2025-05-15 | 2025-05-20 | 2025-07-03 | 2025-07-07 | 2025-07-20 | 2025-07-25 | 2025-08-02 | 2025-08-15 | 2025-08-20 | 2025-08-25
| 117 | Building staff capacity to effectively utilize the electronic document management system (DMS) for improved knowledge organization and retrieval. | AUC/PAPS/CMD/CS/011 | CS | RFB | LC | 60000 | PB-JFA02 | 2025-07-30 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-19 | 2025-08-24 | 2025-08-29 | 2025-09-03 | 2025-09-08 | 2025-09-13
| 118 | Implementation of streamlined PAPS Knowledge Management system and practices (Stakeholders sensitization workshop to strengthen Knowledge Management (KM) systems and practices within DPAPS) | AUC/PAPS/CMD/CS/012 | CS | RFB | LC | 100000 | PB-JFA02 | 2025-07-30 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-19 | 2025-08-24 | 2025-08-29 | 2025-09-03 | 2025-09-08 | 2025-09-13
| 119 | Hiring Consultants to develop a strategy to operationalize online and offline platforms (websites, social medias, etc.) for capturing best practice and lessons learned on AU PCRD Policy implementation | AUC/PAPS/PCRD/CS/001 | CS | INDV | OC | 28000 | IP & MS | 2025-05-22 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-01 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-06
| 120 | Hiring Consultants to publish policy briefs/papers on AU PCRD and peacebuilding experiences, the AU Journal, best practices and lessons learned | AUC/PAPS/PCRD/CS/002 | CS | INDV | OC | 17400 | JFA-PAPS | 2025-06-22 | 2025-06-27 | 2025-07-12 | 2025-07-27 | 2025-08-01 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-06
| 121 | Hiring Consultants to develop guidelines/manuals on PCRD & Peacebuilding with the aim of supporting countries in conflict, post-conflict and political transition contexts | AUC/PAPS/PCRD/CS/003 | CS | INDV | OC | 30000 | JFA-PAPS | 2025-06-22 | 2025-06-27 | 2025-07-12 | 2025-07-27 | 2025-08-01 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-06
| 122 | Hiring Consultants to develop an AU Coordination/Partnership Plan and Standard Operating Procedures for effective implementation of the AU revised PCRD Policy | AUC/PAPS/PCRD/CS/004 | CS | INDV | OC | 23500 | JFA-PAPS | 2025-05-22 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-01 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-06
| 123 | Hiring Consultants to support the revitalization of the African Solidarity Initiative (ASI) especially in the implementation of the AU revised PCRD Policy in relevant contexts | AUC/PAPS/PCRD/CS/005 | CS | INDV | OC | 25000 | JFA-PAPS | 2025-06-22 | 2025-06-27 | 2025-07-12 | 2025-07-27 | 2025-08-01 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-06
| 124 | Hiring of Consultants to develop the Strategic Guidance Framework of the AU PCRD Centre | AUC/PAPS/PCRD/CS/006 | CS | INDV | OC | 50000 | ERM | 2025-04-05 | 2025-04-10 | 2025-04-15 | 2025-04-20 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-05-10 | 2025-05-15 | 2025-05-30
| 125 | Short term consultancy-Analysis of existing climate change strategies and NDCs in RECs and selected AU member States in order to produce a report and policy brief on Africa’s priority areas of action (thematic), status of implementation, challenges and gaps (GCCA+) | AUC/SEBE/CS/001 | CS | INDV | OC | 20000 | EU(100%) | 2025-01-06 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 126 | Short term consultancy- Developing a monitoring and reporting framework for the implementation of the Paris Agreement and climate actions in Africa through a common reporting, monitoring and reporting framework and support in transferring the tool to an online platform (GCCA+) | AUC/SEBE/CS/002 | CS | INDV | OC | 30000 | EU (100%) | 2025-01-06 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 127 | Short term consultancy-Assessment of climate finance flows in RECs and MS(GCCA+) | AUC/SEBE/CS/003 | CS | INDV | OC | 5000 | EU (100%) | 2025-01-06 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 128 | Short-term consultant-Conduct an analysis of 3 NDCs in ECCAS Region and develop a database on the ECCAS Region's NDCs(GCCA+) | AUC/SEBE/CS/004 | CS | INDV | OC | 20000 | EU (100%) | 2025-01-06 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 129 | Short term consultancy- Assessment of climate finance flows in the ECCAS region (GCCA+). | AUC/SEBE/CS/005 | CS | INDV | OC | 5000 | EU (100%) | 2025-01-06 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 130 | Consultancy firm- Develop criteria for the selection of pilot projects, provide technical guidance on the identification of pilot projects and support implementation of Pilot projects at ECCAS Region (GCCA+). | AUC/SEBE/CS/006 | CS | QCBS | OC | 15000 | EU (100%) | 2025-01-06 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 131 | ClimSA Services (Tecnavia) | AUC/SEBE/CS/007 | CS | INDV | OC | 3500000 | EU (100%) | 2025-01-29 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 132 | ClimSa Technical Assistance (AESA) | AUC/SEBE/CS/008 | CS | INDV | OC | 1000000 | EU (100%) | 2025-03-14 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 133 | Consultancy services for ClimSA project on synergy, technical, procurement, meteorological services, climate services (ClimSA) | AUC/SEBE/CS/009 | CS | INDV | OC | 100000 | EU (100%) | 2025-01-24 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 134 | Consultancy services to develop and implement the monitoring & evaluation and reporting system for the ECCAS region - ClimSA | AUC/SEBE/CS/010 | CS | INDV | OC | 18000 | EU (100%) | 2025-02-05 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 135 | Consultancy services to develop the ECCAS Regional Framework for Climate Services - ClimSA | AUC/SEBE/CS/011 | CS | INDV | OC | 18000 | EU (100%) | 2025-02-17 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 136 | ClimSA consultancy services to enage specialised technical experts to support designation of the climate centre, and climate services development at ECCAS | AUC/SEBE/CS/012 | CS | INDV | OC | 90000 | EU (100%) | 2025-06-16 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 137 | ClimSA consultancy services to develop the communication and visibility strategy for the ECCAS region | AUC/SEBE/CS/013 | CS | INDV | OC | 15000 | EU (100%) | 2025-03-20 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 138 | Softwares for ClimSA programme management, monitoring, and reporting software, etc. | AUC/SEBE/CS/014 | CS | INDV | OC | 30000 | EU (100%) | 2025-04-16 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 139 | Consultancy services to develop the African meteorological Atlas - ClimSA | AUC/SEBE/CS/015 | CS | INDV | OC | 36000 | EU (100%) | 2025-05-07 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 140 | Short Term Consultancy - Develop Environmental Impact Assessment Guidelines (Blue Economy) | AUC/SEBE/CS/016 | CS | INDV | OC | 30000 | JFA | 2025-01-20 | 2025-01-15 | 2025-01-26 | 2025-02-16 | 2025-02-23 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28
| 141 | Short Term consultancy - Develop a Framework for conservation and sustainable management of marine resources to combat marine pollution | AUC/SEBE/CS/017 | CS | INDV | DC | 40000 | MEA III | 2025-01-20 | 2025-01-30 | 2025-02-10 | 2025-03-03 | 2025-03-07 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 2025-04-15 | 2025-05-01
| 142 | Short-term consultancy- Assessment on direct and indirect impacts of the aquactic and terrestrial wild meat | AUC/SEBE/CS/018 | CS | INDV | DC | 30000 | MEA III | 2025-01-20 | 2025-01-30 | 2025-02-10 | 2025-03-03 | 2025-03-07 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 2025-04-15 | 2025-05-01
| 143 | Short Term consultancy - Develop an Integrated Waste Management Strategy for Africa | AUC/SEBE/CS/019 | CS | QCBS | RFP | 30000 | MEA III | 2025-01-20 | 2025-01-30 | 2025-02-10 | 2025-03-03 | 2025-03-07 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 2025-04-15 | 2025-05-01
| 144 | short Term consultancy -develop action plan for the domestication of global framework on chemicals and waste | AUC/SEBE/CS/020 | CS | INDV | DC | 20000 | MEA III | 2025-01-20 | 2025-01-30 | 2025-02-10 | 2025-03-03 | 2025-03-07 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 2025-04-15 | 2025-05-01
| 145 | Short Term consultancy - Develop M&E Framework, Communications Plan and Resource Mobilisation Strategy for the Africa Biodiversity Strategy and Action Plan | AUC/SEBE/CS/021 | CS | INDV | DC | 50000 | MEA III | 2025-01-20 | 2025-01-30 | 2025-02-10 | 2025-03-03 | 2025-03-07 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 2025-04-15 | 2025-05-01
| 146 | Develop the 4th Africa Biennial Report on DRR | AUC/SEBE/CS/022 | CS | FIRM | OC | 150000 | EU(100%) | 2025-02-01 | 2025-04-07 | 2025-04-11 | 2025-04-14 | 2025-04-18 | 2025-04-21 | 2025-04-25 | 2025-04-28 | 2025-05-08 | 2025-05-11
| 147 | Finalize Roadmap to support in Establishment Network of Centre for Excellence for DRR and the 3CMDPR | AUC/SEBE/CS/023 | CS | INDV | OC | 50000 | EU(100%) | 2025-03-30 | 2025-04-04 | 2025-04-07 | 2025-04-11 | 2025-04-14 | 2025-04-18 | 2025-04-20 | 2025-04-24 | 2025-04-27 | 2025-05-03
| 148 | Consultancy Services: Development of an AU policy for mainstreaming DRR and CCA in AU programmes and projects | AUC/SEBE/CS/024 | CS | INDV | OC | 100000 | AfDB | 2025-01-15 | 2025-03-30 | 2025-04-07 | 2025-04-10 | 2025-04-14 | 2025-04-17 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 31/04/2025
| 149 | Hire a consultant to prepare AIP PIDA scorecard report and support monitoring, reporting and sharing lessons among Member States and RECs on water and sanitation. | AUC/SEBE/CS/025 | CS | QCBS | OC | 50000 | EU/TEI (100%) | 2025-01-15 | 2025-03-30 | 2025-04-07 | 2025-04-10 | 2025-04-14 | 2025-04-17 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 31/04/2025
| 150 | Hire a consultant to facilitate the development of Post 2025 Africa Water and Sanitation Policy | AUC/SEBE/CS/026 | CS | QCBS | OC | 50000 | EU/TEI (100%) | 2025-01-15 | 2025-03-30 | 2025-04-07 | 2025-04-10 | 2025-04-14 | 2025-04-17 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 31/04/2025
| 151 | Hire a consultant to design regional and continental investments programs on water and sanitation, and to provide technical support to Member States and RECs in preparing project portfolios and pipelines, | AUC/SEBE/CS/027 | CS | QCBS | OC | 100000 | EU/TEI (100%) | 2025-01-15 | 2025-03-30 | 2025-04-07 | 2025-04-10 | 2025-04-14 | 2025-04-17 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 31/04/2025
| 152 | Strengthen the Coordination capacity of African Union on water governance through staff deployment to water unit - Water and Climate Adviser and Project Coordinator | AUC/SEBE/CS/028 | CS | QBS | OC | 144000 | EU/TEI (100%) | 2025-02-17 | 2025-01-15 | 2025-02-14 | 2025-03-07 | 2025-03-14 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16
| 153 | Strengthen the Coordination capacity of African Union on water governance through staff deployment to water unit - Water Policy Adviser | AUC/SEBE/CS/029 | CS | QBS | OC | 96000 | EU/TEI (100%) | 2025-06-16 | 2025-01-15 | 2025-02-14 | 2025-03-07 | 2025-03-14 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16
| 154 | Strengthen the Coordination capacity of African Union on water governance through staff deployment to water unit - Finance and Administrative Assistant (GS4) | AUC/SEBE/CS/030 | CS | QBS | OC | 18762 | EU/TEI (100%) | 2025-03-20 | 2025-01-15 | 2025-02-14 | 2025-03-07 | 2025-03-14 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16
| 155 | Consultancy Services: Development of an AU policy for mainstreaming DRR and CCA in AU programmes and projects | AUC/SEBE/CS/031 | CS | INDV | OC | 100000 | AfDB | 2025-04-16 | 2025-03-30 | 2025-04-07 | 2025-04-10 | 2025-04-14 | 2025-04-17 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 31/04/2025
| 156 | Hydromet Diagnostics Study (AMHEWAS) | AUC/SEBE/CS/032 | CS | INDIV | OC | 100000 | WB | 2025-05-07 | 2025-02-15 | 2025-04-11 | 2025-04-14 | 2025-04-18 | 2025-04-21 | 2025-04-25 | 2025-04-28 | 2025-05-08 | 2025-05-11
| 157 | Consultancy services to support development of biennial report with focus on water-related disasters (AMHEWAS) | AUC/SEBE/CS/033 | CS | INDIV | OC | 70000 | WB | 2025-05-07 | 2025-02-15 | 2025-04-07 | 2025-04-11 | 2025-04-14 | 2025-04-18 | 2025-04-20 | 2025-04-24 | 2025-04-27 | 2025-05-03
| 158 | Development of AMHEWAS platform | AUC/SEBE/CS/034 | CS | INDIV | OC | 70000 | Denmark | 2025-01-15 | 2025-03-15 | 2025-04-07 | 2025-04-10 | 2025-04-14 | 2025-04-17 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 31-04-2025
| 159 | Development of Anticipatory Action guidelines | AUC/SEBE/CS/035 | CS | INDIV | OC | 42000 | Denmark | 2025-01-15 | 2025-03-15 | 2025-04-11 | 2025-04-14 | 2025-04-18 | 2025-04-21 | 2025-04-25 | 2025-04-28 | 2025-05-08 | 2025-04-25
| 160 | To develop an integrated Land Use Management Plan (ILUMP) for the northern wildlife connectivity landscapes between the Serengeti-Ngorongoro, the Tarangire-Manyara and the ArushaKilimanjaro-Mkomazi ecosystems. | AUC/SEBE/CS/036 | CS | INDV | OC | 30000 | MS | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 161 | Development of Knowledge Products (Annual SDGEA reports, Annual State of Women’s Rights Report, Maputo Protocol and Index etc) | AUC/WGYD/CS/001 | CS | QCBS | OC | 18000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 162 | Annual AU Gender Scorecard development | AUC/WGYD/CS/002 | CS | QCBS | OC | 9000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 163 | Support the implementation of the AU Gender Observatory (AUGO) | AUC/WGYD/CS/003 | CS | QCBS | OC | 9000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 164 | Annual training of Gender Focal Points on Gender & Youth Mainstreaming Guidelines & Scoreboard | AUC/WGYD/CS/004 | CS | QCBS | OC | 3000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 165 | Implement the Gender and Youth Mainstreaming Campaign | AUC/WGYD/CS/005 | CS | QCBS | OC | 3000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 166 | Development of the African Women Decade on Financial and Economic Inclusion (AWD-FEI) Knowledge Products | AUC/WGYD/CS/006 | CS | QCBS | OC | 50000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 167 | Development and publish One mIllion Next level scorecard | AUC/WGYD/CS/007 | CS | QCBS | OC | 20000 |  | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 168 | Develop and Publish African Youth Charter @20 Youth Engagement strategy and toolkit | AUC/WGYD/CS/008 | CS | QCBS | OC | 20000 |  | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 169 | AU Young Professional Program framework and capacity building toolkit | AUC/WGYD/CS/009 | CS | QCBS | OC | 10000 |  | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 170 | Regional Programme Coordinator | AUC/WGYD/CS/010 | CS | QCBS | OC | 72000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 171 | Project Officer | AUC/WGYD/CS/011 | CS | QCBS | OC | 60000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 172 | Project Officer - CIEFFA | AUC/WGYD/CS/012 | CS | QCBS | OC | 54000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 173 | Finance Officer | AUC/WGYD/CS/013 | CS | QCBS | OC | 31500 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 174 | Finance Assistant - CIEFFA | AUC/WGYD/CS/014 | CS | QCBS | OC | 42000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 175 | Procurement Specialist | AUC/WGYD/CS/015 | CS | QCBS | OC | 42000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 176 | Environmental and Social Specialist | AUC/WGYD/CS/016 | CS | QCBS | OC | 42000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 177 | Communications Officer | AUC/WGYD/CS/017 | CS | QCBS | OC | 31500 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 178 | Support the implementation of the AU EVAWG Campaign and the AUCEVAWG | AUC/WGYD/CS/018 | CS | QCBS | OC | 30000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 179 | System Costs (Contract Management System/ Electronic Voting system) | AUC/OLC/CS/001 | CS | QCBS | DC | 100000 | MS | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 180 | Consultancy Services from a Company for Indesign, Infographics, Structuring and Printing of 2025 Annual Report | AUC/ODG/CS/001 | CS | QCBS | LC | 15000 | MS(100%) | 2025-08-01 | 2025-08-15 | 2025-08-18 | 2025-08-17 | 2025-08-18 | 2025-08-20 | 2025-08-22 | 2025-08-25 | 2025-08-27 | 2025-08-29
| 181 | Hire Consultancy Services to support the deployment of Solution | AUC/HRM/CS/001 | CS | QCBS | OC | 6400 | WB - Biashara | 2025-06-12 | 2025-06-17 | 2025-07-17 | 2025-08-07 | 2025-08-14 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16
| 182 | Hire Consultancy Services to Develop and implement integrated talent management framework | AUC/HRM/CS/002 | CS | QCBS | OC | 1800 | JPA | 2025-08-15 | 2025-08-20 | 2025-09-10 | 2025-10-01 | 2025-10-08 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10
| 183 | Hire Consultancy Services to Revamp training curriculum on performance management and deploy trainings | AUC/HRM/CS/003 | CS | QCBS | OC | 30000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 184 | Hire consultancy services to support development of online courses in at least 2 languages French and English | AUC/HRM/CS/004 | CS | QCBS | OC | 19000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 185 | Hire consultancy services to support development of online courses in at least 2 languages French and English | AUC/HRM/CS/005 | CS | QCBS | OC | 15000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10
| 186 | Hire consultancy Services to communicate survey results | AUC/HRM/CS/006 | CS | QCBS | OC | 12000 | WB - Biashara | 2025-08-15 | 2025-08-20 | 2025-08-27 | 2025-09-17 | 2025-09-24 | 2025-10-15 | 2025-11-05 | 2025-11-26 | 2025-12-17 | 2026-01-07
| 187 | Hire consultancy services to revamp training curriculum on performance management and deploy trainings - AU Academy | AUC/HRM/CS/007 | CS | QCBS | OC | 20000 | WB - Biashara | 2025-08-15 | 2025-08-20 | 2025-08-27 | 2025-09-17 | 2025-09-24 | 2025-10-15 | 2025-10-22 | 2025-11-12 | 2025-11-19 | 2025-12-10
| 188 | Hire consultancy services to provide Spanish Trainings for the Union | AUC/HRM/CS/008 | CS | QCBS | OC | 20000 | Spain | 2025-08-15 | 2025-08-20 | 2025-08-27 | 2025-09-17 | 2025-09-24 | 2025-10-15 | 2025-10-22 | 2025-11-12 | 2025-11-19 | 2025-12-10
| 189 | Hiring of Consultants to provide Electoral Assistance (Technical Assistance) to EMBs through Training, Expert Deployment, Peer Learning, and Networks Strengthening to Member States | AUC/PAPS/GCPD/CS/001 | CS | INDV | LC | 50000 | EU & JPA (100%) | 2025-04-12 | 2025-04-17 | 2025-05-17 | 2025-06-07 | 2025-06-14 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17
| 190 | Hiring of Consultants/Experts to Adopt the Technical Assistance Guide for EOP/EOM | AUC/PAPS/GCPD/CS/002 | CS | INDV | LC | 10000 | EU & JPA (100%) | 2025-04-18 | 2025-04-23 | 2025-05-23 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23
| 191 | Hiring of Consultants/Experts to conduct trainings to Electoral Experts, Long Term and Short Term Observers | AUC/PAPS/GCPD/CS/003 | CS | INDV | LC | 50000 | EU & JPA (100%) | 2025-04-12 | 2025-04-17 | 2025-05-17 | 2025-06-07 | 2025-06-14 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17
| 192 | Hiring of Consultants to develop the African Charter on Housing, Urban Development and Human Settlements or a Model law for Housing, Urbanization and Human Settlement in Africa | AUC/PAPS/GCPD/CS/004 | CS | INDV | OC | 30000 | MS (100%) | 2025-05-13 | 2025-05-18 | 2025-06-17 | 2025-07-08 | 2025-07-15 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17
| 193 | Hiring of Training Facilitators/Experts for Technical Assistance and Core Team to conduct Election Observation in the Continent | AUC/PAPS/GCPD/CS/005 | CS | INDV | LC | 65000 | EU & JPA (100%) | 2025-05-14 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-05-01
| 194 | Hiring of Consultants for the establishments of African Union Human Rights Memorial Virtual project | AUC/PAPS/GCPD/CS/006 | CS | INDV | OC | 30000 | MS | 2025-05-15 | 2025-05-20 | 2025-06-19 | 2025-07-10 | 2025-07-17 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19
| 195 | Hiring of Consultants for Technical Assistance to AU Member States on the Implemetation of AU Transitional Justice Policy | AUC/PAPS/GCPD/CS/007 | CS | INDV | OC | 60000 | MS | 2025-05-02 | 2025-05-07 | 2025-06-06 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06
| 196 | Hiring of Consultants to support the Implementation of the AU Ten-years Action plan | AUC/PAPS/GCPD/CS/008 | CS | INDV | OC | 40000 | MS | 2025-06-02 | 2025-06-07 | 2025-07-07 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06
| 197 | Hiring of Consultants for the Resource Centre on Goverance, Democracy, Human Rights and Election | AUC/PAPS/GCPD/CS/009 | CS | INDV | OC | 18000 | MS | 2025-06-02 | 2025-06-07 | 2025-07-07 | 2025-07-28 | 2025-08-04 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06
| 198 | Hiring of Consutants for technical Assistance to ACDEG State Parties implimentation and Report Development | AUC/PAPS/GCPD/CS/010 | CS | INDV | OC | 18000 | EU-AUSPIV | 2025-04-04 | 2025-04-09 | 2025-05-09 | 2025-05-30 | 2025-06-06 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09
| 199 | Deploy a Team of Experts to AU Member States ( 6 -12 months each) to enhance national/RECs expertise in the implementation of SSR processes to prevent conflicts and rebuild national cohesion | AUC/PAPS/GCPD/CS/011 | CS | INDV | OC | 38112 | MS | 2025-05-15 | 2025-05-20 | 2025-06-14 | 2025-06-29 | 2025-07-06 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-08-06
| 200 | Recruit Consultants to support the process to revise the OAU Convention on Mercenarism | AUC/PAPS/GCPD/CS/012 | CS | INDV | OC | 24000 | MS | 2025-05-15 | 2025-05-20 | 2025-06-14 | 2025-06-29 | 2025-07-06 | 2025-07-11 | 2025-07-18 | 2025-07-23 | 2025-07-30 | 2025-08-06
| 201 | Deploy Experts to Lesotho and Madagascar for a minimum of three (3) months each to support National Security Sector Reform processes | AUC/PAPS/GCPD/CS/013 | CS | INDV | OC | 36000 | JFA- PAPS | 2025-05-15 | 2025-05-20 |  | 1900-01-29 | 1900-02-08 | 1900-02-23 | 1900-03-25 | 1900-04-24 | 1900-05-25 | 1900-06-29
| 202 | Recruit Consultants to support identified AU MS to review and update existing national laws on arms control | AUC/PAPS/GCPD/CS/014 | CS | INDV | OC | 24000 | MS | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29
| 203 | Recruit Consultants to draft an AU guideline on SSR and Mediation as well as on SALW & DDR | AUC/PAPS/GCPD/CS/015 | CS | INDV | OC | 25000 | JFA - PAPS & Spain | 2025-05-15 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-06-24 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-30
| 204 | Hiring of Experts for Capacity Building on Human and Peoples' Rights | AUC/PAPS/GCPD/CS/016 | CS | INDV | LC | 25000 | JFA- PAPS | 2025-02-28 | 2025-03-05 | 2025-04-04 | 2025-05-15 | 2025-06-20 | 2025-07-25 | 2025-09-27 | 2025-10-30 | 2025-11-10 | 2025-12-10
| 205 | Hiring of Consultants for Technical Assistance, Capacity Building, and to realize Study on Human and Peoples' Rights | AUC/PAPS/GCPD/CS/017 | CS | INDV | OC | 25000 | JFA- PAPS | 2025-02-28 | 2025-03-05 | 2025-04-04 | 2025-05-15 | 2025-06-20 | 2025-07-25 | 2025-09-27 | 2025-10-30 | 2025-11-10 | 2025-12-10
| 206 | Recruitment of Consultants or Consultant Firm for the state of public service performance in Africa | AUC/PAPS/GCPD/CS/018 | CS | INDV | OC | 25000 | JFA- PAPS & WB | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29
| 207 | Recruitment of Consultants for the SPAT Capacity Building Programs | AUC/PAPS/GCPD/CS/019 | CS | INDV | LC | 25000 | WB | 2025-05-15 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-06-24 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-30
| 208 | Recruitment of consultants for the Pan African Decentralisation Programme Award | AUC/PAPS/GCPD/CS/020 | CS | INDV | OC | 25000 | JFA- PAPS | 2025-05-22 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-01 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-06
| 209 | Hiring Three DDR consultants to support Ethiopia in the implementation of the COHA peace agreement under the ERM process. | AUC/PAPS/GCPD/CS/021 | CS | INDV | OC | 297000 | ERM | 2025-04-05 | 2025-04-10 | 2025-04-15 | 2025-04-20 | 2025-04-25 | 2025-04-27 | 2025-04-30 | 2025-05-10 | 2025-05-15 | 2025-05-30
| 210 | Hiring of Core Team Experts to African Union Election Observation Missions in the AU Member States | AUC/PAPS/GCPD/CS/022 | CS | INDV | OC | 100000 | MS & JFA PAPS | 2025-06-20 | 2025-06-27 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29
| 211 | Deploy Two (2) SSR Experts to AU Member States and RECS to support in the implementation of SSR processes in order to prevent conflicts and rebuild national cohesion | AUC/PAPS/GCPD/CS/023 | CS | INDV | OC | 50000 | JFA PAPS/Spain | 2025-06-21 | 2025-06-29 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29
| 212 | Recruitment of Consultants or Consultant Firm for the State of Public Service Performance & Decentralisation in Africa | AUC/PAPS/GCPD/CS/024 | CS | INDV | OC | 30000 | JFA- PAPS | 2025-06-15 | 2025-06-20 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29
| 213 | Recruitment of Consultants/Thematic Experts for the 2025 Continental Commemoration of the APSD | AUC/PAPS/GCPD/CS/025 | CS | INDV | LC | $10000 | JFA- PAPS | 2025-06-21 | 2025-06-23 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29
| 214 | Recruitment of Consultants/Thematic Experts for the 2025 Continental Commemoration of the APSD | AUC/PRO/CS/001 | CS | INDV | LC | 30000 | MS | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
| 215 | Technical training & Capacity Building of Protocol Staff | AUC/PRO/CS/002 | CS | QCBS | LC | 15794 | MS | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04 | 2025-10-09
| 216 | Recruit consultant to support Representative Office through providing policy guidance and analysis on political matters, and engaging in various stakeholders and partner collaborations including maintaining diplomatic liaisons | AUC/PD/CAI/CS/001 | CS | INDV | OC | 120000 | MS(100%) | 2025-05-08 | 2025-05-13 | 2025-06-12 | 2025-07-03 | 2025-07-10 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12
| 217 | Consultancy Services to Build a toolkit / template on cyber strategies development for use by MS | AUC/IED/CS/001 | CS | INDV | LC | 54000 | WB (100%) | 2025-04-01 | 2025-04-06 | 2025-05-06 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08
| 218 | Consultancy Services to Create a public portal on Child online Safety and Empowerment | AUC/IED/CS/002 | CS | LCS | OC | 108000 | WB (100%) | 2025-04-02 | 2025-04-07 | 2025-05-07 | 2025-05-28 | 2025-06-04 | 2025-06-09 | 2025-06-16 | 2025-06-21 | 2025-06-28 | 2025-07-03
| 219 | Consultancy Services to prepare a Toolkit on key elements of a Draft National Plan and Organise a Continnetal Workshop to accelerate the domestication of AU Strategy on Enabling Environment for Africa's Single Digital Market | AUC/IED/CS/003 | CS | INDV | OC | 144000 | WB (100%) | 2025-04-03 | 2025-04-08 | 2025-05-08 | 2025-05-29 | 2025-06-05 | 2025-06-10 | 2025-06-17 | 2025-06-22 | 2025-06-29 | 2025-07-04
| 220 | Consultancy Services to Conduct yearly regulatory audits and organise national workshops to support the development of of national strategies towards attaining Africa’s Single Digital Market | AUC/IED/CS/004 | CS | INDV | LC | 66000 | WB (100%) | 2025-04-04 | 2025-04-09 | 2025-05-09 | 2025-05-30 | 2025-06-06 | 2025-06-11 | 2025-06-18 | 2025-06-23 | 2025-06-30 | 2025-07-05
| 221 | Consultancy Services to Support AU Member States to conduct regulatory audit / baseline information to accelerate the establishment of Africa's Digital Single Market | AUC/IED/CS/005 | CS | INDV | LC | 96000 | WB (100%) | 2025-04-05 | 2025-04-10 | 2025-05-10 | 2025-05-31 | 2025-06-07 | 2025-06-12 | 2025-06-19 | 2025-06-24 | 2025-07-01 | 2025-07-06
| 222 | Consultancy Services to Support Member States to adopt the minimum standard for the interoperability standard for Africa | AUC/IED/CS/006 | CS | INDV | LC | 36000 | MS (100%) | 2025-04-06 | 2025-04-11 | 2025-05-11 | 2025-06-01 | 2025-06-08 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-07-02 | 2025-07-07
| 223 | Consultancy Services to Establish DTS PIU, conduct midterm evaluation and develop and pilot of Digital Maturity Assessment Toolkit | AUC/IED/CS/007 | CS | LCS | OC | 768000 | WB (100%) | 2025-04-07 | 2025-04-12 | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-06-14 | 2025-06-21 | 2025-06-26 | 2025-07-03 | 2025-07-08
| 224 | Consultancy Services to Pilot the application of developed standards & data categorization model in priority sectors in selected countries for enabling Cross-Border Data Flows | AUC/IED/CS/008 | CS | INDV | LC | 36000 | WB (100%) | 2025-04-08 | 2025-04-13 | 2025-05-13 | 2025-06-03 | 2025-06-10 | 2025-06-15 | 2025-06-22 | 2025-06-27 | 2025-07-04 | 2025-07-09
| 225 | Consultancy Services to Conduct needs assessment and case collection for Cross-Border Data Flows | AUC/IED/CS/009 | CS | INDV | LC | 56160 | WB (100%) | 2025-04-09 | 2025-04-14 | 2025-05-14 | 2025-06-04 | 2025-06-11 | 2025-06-16 | 2025-06-23 | 2025-06-28 | 2025-07-05 | 2025-07-10
| 226 | Consultancy Services to Develop data governance documents and technical standards for fostering Cross-Border Data Flows | AUC/IED/CS/010 | CS | INDV | LC | 46080 | WB (100%) | 2025-04-10 | 2025-04-15 | 2025-05-15 | 2025-06-05 | 2025-06-12 | 2025-06-17 | 2025-06-24 | 2025-06-29 | 2025-07-06 | 2025-07-11
| 227 | Consultancy Services to Develop a Master Plan on National and Regional Data Centers and Sovereign African Cloud | AUC/IED/CS/011 | CS | INDV | LC | 58080 | WB (100%) | 2025-04-11 | 2025-04-16 | 2025-05-16 | 2025-06-06 | 2025-06-13 | 2025-06-18 | 2025-06-25 | 2025-06-30 | 2025-07-07 | 2025-07-12
| 228 | Consultancy Services to Develop and implement a Strategic Plan on Africa Digital Data Value Chains and Market | AUC/IED/CS/012 | CS | INDV | LC | 48000 | WB (100%) | 2025-04-12 | 2025-04-17 | 2025-05-17 | 2025-06-07 | 2025-06-14 | 2025-06-19 | 2025-06-26 | 2025-07-01 | 2025-07-08 | 2025-07-13
| 229 | Consultancy Services to Development of Green Digital Infrastructure Framework | AUC/IED/CS/013 | CS | LCS | OC | 264794 | WB (100%) | 2025-04-13 | 2025-04-18 | 2025-05-18 | 2025-06-08 | 2025-06-15 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-09 | 2025-07-14
| 230 | Consultancy Services to Carry out harmonisation of regional grid codes across the power pools and Establishment of Continental Electricity Regulatory Index | AUC/IED/CS/014 | CS | LCS | LC | 78000 | WB (100%) | 2025-04-14 | 2025-04-19 | 2025-05-19 | 2025-06-09 | 2025-06-16 | 2025-06-21 | 2025-06-28 | 2025-07-03 | 2025-07-10 | 2025-07-15
| 231 | Consultancy Services to Implementation of the continental Solar Policy framework and programme on technology transfer that will enable the Member States to access, manufacture, and adopt clean energy | AUC/IED/CS/015 | CS | INDV | LC | 36000 | EU (100%) | 2025-04-15 | 2025-04-20 | 2025-05-20 | 2025-06-10 | 2025-06-17 | 2025-06-22 | 2025-06-29 | 2025-07-04 | 2025-07-11 | 2025-07-16
| 232 | Consultancy Services to Develop a continental framework and programme on the application of renewable energy in the humanitarian sector as an enabler for peace and security | AUC/IED/CS/016 | CS | INDV | LC | 48000 | EU (100%) | 2025-04-16 | 2025-04-21 | 2025-05-21 | 2025-06-11 | 2025-06-18 | 2025-06-23 | 2025-06-30 | 2025-07-05 | 2025-07-12 | 2025-07-17
| 233 | Consultancy Services to Implementation of policy guidelines and regulatory frameworks for Member States to develop and generate green hydrogen | AUC/IED/CS/017 | CS | LCS | LC | 72000 | EU (100%) | 2025-04-17 | 2025-04-22 | 2025-05-22 | 2025-06-12 | 2025-06-19 | 2025-06-24 | 2025-07-01 | 2025-07-06 | 2025-07-13 | 2025-07-18
| 234 | Consultancy Services to Implementation of guidelines and strategies to mobilize private and public sectors' participation in mini-grids development in Africa and the application for PUE | AUC/IED/CS/018 | CS | INDV | LC | 42000 | EU (100%) | 2025-04-18 | 2025-04-23 | 2025-05-23 | 2025-06-13 | 2025-06-20 | 2025-06-25 | 2025-07-02 | 2025-07-07 | 2025-07-14 | 2025-07-19
| 235 | Consultancy Services for Biashara/SAATM Project coordination and reporting | AUC/IED/CS/019 | CS | INDV | OC | 120000 | EU (100%) | 2025-04-19 | 2025-04-24 | 2025-05-24 | 2025-06-14 | 2025-06-21 | 2025-06-26 | 2025-07-03 | 2025-07-08 | 2025-07-15 | 2025-07-20
| 236 | Consultancy Services to Undertake Consultancy Services for the development of air cargo/trade routes to support the operationalization of SAATM | AUC/IED/CS/020 | CS | LCS | LC | 90000 | WB (100%) | 2025-04-20 | 2025-04-25 | 2025-05-25 | 2025-06-15 | 2025-06-22 | 2025-06-27 | 2025-07-04 | 2025-07-09 | 2025-07-16 | 2025-07-21
| 237 | Consultancy Services to develop seamless airspace, Air Navigation Services Architecture to support SAATM | AUC/IED/CS/021 | CS | LCS | OC | 150000 | WB (100%) | 2025-04-21 | 2025-04-26 | 2025-05-26 | 2025-06-16 | 2025-06-23 | 2025-06-28 | 2025-07-03 | 2025-07-08 | 2025-07-13 | 2025-07-18
| 238 | GRMF Procurement Officer | AUC/IED/CS/022 | CS | INDV | LC | 72000 | WB (100%) | 2025-04-22 | 2025-04-27 | 2025-05-27 | 2025-06-17 | 2025-06-24 | 2025-06-29 | 2025-07-04 | 2025-07-09 | 2025-07-14 | 2025-07-19
| 239 | GRMF Project/Legal Officer | AUC/IED/CS/023 | CS | INDV | LC | 72000 | MS (100%) | 2025-04-23 | 2025-04-28 | 2025-05-28 | 2025-06-18 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20
| 240 | Consultancy Services for the Evaluation and Further Development of the Geothermal Risk Mitigation Facility (GRMF) Regional Coordinating Unit (RGCU) | AUC/IED/CS/024 | CS | INDV | OC | 2000000 | KFW (100%) | 2025-04-24 | 2025-04-29 | 2025-05-29 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31
| 241 | Individual Consultant to support AUC in the implementation of AfSEM | AUC/IED/CS/025 | CS | INDV | LC | 72000 | KFW (100%) | 2025-04-25 | 2025-04-30 | 2025-05-30 | 2025-06-20 | 2025-06-27 | 2025-07-02 | 2025-07-07 | 2025-07-12 | 2025-07-17 | 2025-07-22
| 242 | Recurtment of a M&E consultant for the DTFA-WARDIP Project | AUC/IED/CS/026 | CS | INDV | LC | 60000 | EU (100%) | 2025-04-26 | 2025-05-01 | 2025-05-06 | 2025-05-11 | 2025-05-16 | 2025-05-21 | 2025-05-26 | 2025-05-31 | 2025-06-05 | 2025-06-10
| 243 | Technical Project advisor | AUC/PMRM/CS/001 | CS | INDV | LC | 90000 | WB (100%) | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29
| 244 | Technical Project Coordinator | AUC/PMRM/CS/002 | CS | INDV | LC | 80000 | WB | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03
| 245 | Communicatiion Specialist | AUC/PMRM/CS/003 | CS | INDV | LC | 70000 | WB | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03
| 246 | Project Officer | AUC/PMRM/CS/004 | CS | INDV | LC | 60000 | WB | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03
| 247 | Project Admin Assistant | AUC/PMRM/CS/005 | CS | INDV | LC | 40000 | WB | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25
| 248 | Procurement Specialist | AUC/PMRM/CS/006 | CS | INDV | LC | 60000 | WB | 2024-09-01 | 2024-09-08 | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-10-06 | 2024-10-13 | 2024-10-20 | 2024-10-27 | 2024-11-03
| 249 | Financial Statement Specialist | AUC/PMRM/CS/007 | CS | INDV | LC | 60000 | WB | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 250 | selection Process of Think Tanks | AUC/PMRM/CS/008 | CS | INDV | LC | 50000 | WB | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10
| 251 | Establish a database | AUC/PMRM/CS/009 | CS | FIRM | OC | 110720 | WB | 2025-08-01 | 2025-08-08 | 2025-08-13 | 2025-08-18 | 2025-08-23 | 2025-08-28 | 2025-09-02 | 2025-09-07 | 2025-09-12 | 2025-09-17
| 252 | Coordinating the fellowship and secondment program | AUC/PMRM/CS/010 | CS | FBS | OC | 102572 | WB | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03
| 253 | Conduct a scoping exercise | AUC/PMRM/CS/011 | CS | INDV | LC | 21696 | WB | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03
| 254 | Repository establishment | AUC/PMRM/CS/012 | CS | FIRM | OC | 118000 | WB | 2025-11-16 | 2025-11-23 | 2025-11-28 | 2025-12-03 | 2025-12-08 | 2025-12-13 | 2025-12-18 | 2025-12-23 | 2025-12-28 | 2026-01-02
| 255 | Support the call for the research proposal | AUC/PMRM/CS/013 | CS | INDV | OC | 48000 | WB | 2025-05-01 | 2025-05-06 | 2025-05-11 | 2025-05-16 | 2025-05-21 | 2025-05-26 | 2025-05-31 | 2025-06-05 | 2025-06-10 | 2025-06-15
| 256 | Organize the review of policy papers | AUC/PMRM/CS/014 | CS | INDV | OC | 54000 | WB | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05
| 257 | Establishing capacity to operate a sustainable policy making platform | AUC/PMRM/CS/015 | CS | FBS | OC | 6000000 | WB | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05
| 258 | Strengthen TTs and MS in data measurement & foresight analysis | AUC/PMRM/CS/016 | CS | FIRM | OC | 391869 | WB | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03
| 259 | Selection of consultant for design of resourceMobilization strategy | AUC/PMRM/CS/017 | CS | FIRM | OC | 100000 | WB | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
| 260 | Selection of consultant to conduct a feasibility study for the endowment fund | AUC/PMRM/CS/018 | CS | INDV | OC | 50000 | WB | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
| 261 | Consultancy services for OSAKA Expo 2025 | AUC/PMRM/CS/019 | CS | LCS | OC | 30000 | China and MS | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10
| 262 | Consultancy Services for implementation of phase III Partnership and Resource Mobilization Management Information System (PReMIS). | AUC/PMRM/CS/020 | CS | LCS | OC | 25000 | AfDB-ICBC (100%) | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16
| 263 | Create Data Driven Organization for a better-informed decision making | AUC/MISD/CS/001 | CS | QCBS | OC | 120000 | WB | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 264 | Create Data-Fluent Organization for a consolidated view of historical and current data | AUC/MISD/CS/002 | CS | QCBS | OC | 143245 | WB | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 265 | Create digitally transformed organization for reimaging operation through technology | AUC/MISD/CS/003 | CS | QCBS | OC | 200000 | JFA (Basket Fund) | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 266 | Enhance Data Center Capacity - Enhanced Network operation Center | AUC/MISD/CS/004 | CS | QCBS | OC | 150000 | WB | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 267 | Undertake evaluation and monitoring Strategy and Development | AUC/MISD/CS/005 | CS | QCBS | OC | 254658 | WB | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 268 | Capacity building End users | AUC/MISD/CS/006 | CS | QCBS | OC | 40000 | MS | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 269 | Conduct Capacity Building training for MIS Directorate | AUC/MISD/CS/007 | CS | QCBS | OC | 40000 | MS | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
| 270 | Consultancy services forimplementation of communication equipment for occ building and computer-aided facilities management (CAFM) system | AUC/AFMD/CS/001 | CS | INDV | OC | 50000 | MS | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-06-10 | 2025-06-15 | 2025-06-20
37647785.46
Formulas:
Invitation Date = [Request Submission Date]+5
Opening Date = [Invitation Date]+30
Evaluation Date = [Opening Date]+21
Approval Date = [Evaluation Date]+7
Opening of Financial Proposal = [Approval Date]+5
Combined Evaluation = [Opening of Financial Proposal]+7

## Non Consultancy
AFRICAN UNION ANNUAL PROCUREMENT PLAN AS OF AUGUST 2025
NON-CONSULTANCY SERVICES
| S/N | Description | Reference Nnumber | Category Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
| 1 | Audit services (Under Framework Contract) | AUC/ARD/NC/001 | NC | RFQ | LC | 65000 | IBAR(9.23%) GF(33.84%) EU(41,53%) SIDA(15.38) | 2025-02-01 | 2025-02-06 | 2025-02-02 | 2025-02-07 | 2025-02-03 | 2025-02-08 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07
| 2 | Framework contracts for provision of interpretation, conference and catering facilities in to AU-IBAR Nairobi | AUC/ARD/NC/002 | NC | RFB | OC | 700000 | EU(44.07%) GF(37.28%) SIDA(15.07%) IBAR(3.57%) | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 3 | Provision of cleaning, janitorial and landscaping services | AUC/ARD/NC/003 | NC | RFB | OC | 48000 | IBAR(39.58%) MS(39.58%) EU(8.33%) SIDA(4.16%) | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 4 | Maintenance of AU-IBAR AFADATA database | AUC/ARD/NC/004 | NC | RFP | OC | 40000 | EU | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 5 | Printing of 1000 copies of the AU Commodity Starategy | AUC/ETTIM/NC/001 | NC | RFQ | LC | 36000 | MS(100%) | 2025-07-01 | 2025-07-06 | 2025-07-13 | 2025-08-03 | 2025-08-10 | 2025-08-31 | 2025-09-07 | 2025-09-28 | 2025-10-05 | 2025-10-12
| 6 | Printing of 1000 copies of the ETTIM Annual Report | AUC/ETTIM//NC/002 | NC | RFQ | LC | 30000 | MS(100%) | 2025-09-01 | 2025-09-06 | 2025-09-13 | 2025-10-04 | 2025-10-11 | 2025-11-01 | 2025-11-08 | 2025-11-29 | 2025-12-06 | 2025-12-13
| 7 | Communication Campaign to promote investment and trade through Made in Africa Campaign, Buy Africa Build Africa, Operational Instruments | AUC/ICD/NC/001 | NC | RFP | OC | 40500 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 8 | AU Media Fellowship catering, transport, etc.… | AUC/ICD/NC/002 | NC | RFQ | LC | 20000 | MS(100%) | 2025-03-18 | 2025-03-23 | 2025-03-30 | 2025-04-20 | 2025-04-27 | 2025-05-18 | 2025-05-25 | 2025-06-15 | 2025-06-22 | 2025-07-13
| 9 | Maintenance of Medical Equipment(Framework Contracts) | AUC/MHSD/NC/001 | NC | RFB | OC | 236206 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-04-04 | 2025-04-25 | 2025-05-16 | 2025-06-06 | 2025-06-27 | 2025-07-18
| 10 | Hands on training of the staff in tandem to run the new equipment/services | AUC/MHSD/NC/002 | NC | RFQ | OC | 30000 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-04-04 | 2025-04-25 | 2025-05-16 | 2025-06-06 | 2025-06-27 | 2025-07-18
| 11 | Upgrade of telemedicine and Continuing Medical Education facility | AUC/MHSD/NC/003 | NC | RFQ | OC | 100000 | MS(100%) | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10
| 12 | Participating in Experience and knowledge sharing and benchmarking workshops/ attachment with similar institutions | AUC/MHSD/NC/004 | NC | RFQ | OC | 50000 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 13 | Implement an Audit management systems (computer-assisted audit techniques) Procurement of TeamMate Audit Management System and related licenses | AUC/OIO/NC/001 | NC | RFQ | LC | 100000 | JFA(Bucket Fund) (100%) | 2025-01-30 | 2025-02-04 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07
| 14 | Quality management systems of the OIO Upgrade of the OIO Investigation Case Mgt Software | AUC/OIO/NC/002 | NC | RFQ | DC | 56000 | JFA(Bucket Fund) (100%) | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10
| 15 | Conduct Internal and External Sensitization Workshops A) OIO Staff workshop /retreat (Procurement of hotel, travel, and Consultancy services) B) External stakeholder engagement workshops (Procurement of hotel, travel, and Consultancy services) | AUC/OIO/NC/003 | NC | QCBS | LC | 160000 | MS(31%) IPs(69%) | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26
| 16 | FRAMEWORK CONTRACT FOR TRAVEL MANAGEMENT COMPANY | AUC/OSSD/NC/001 | NC | RFB | OC | 0 | MS | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 17 | Maintainance of Safety and Security systems | AUC/OSSS/NC/001 | NC | RFQ | LC | 150000 | MS (100%) | 2025-01-21 | 2025-01-26 | 2025-02-02 | 2025-02-23 | 2025-03-02 | 2025-03-23 | 2025-03-30 | 2025-04-20 | 2025-04-27 | 2025-05-18
| 18 | Procurement of an Integrated Assets and Warehouse Management systemincluding workflow for the AUCLB. | AUC/PAPS/CMD/NC/001 | NC | RFQ | LC | 60000 | South Korea | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-22 | 2025-06-12 | 2025-07-03 | 2025-07-10
| 19 | Shipment of Equipment and materials from to AUCLB in 2025. | AUC/PAPS/CMD/NC/002 | NC | RFQ | LC | 1000000 | MS(100%) | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29 | 2025-06-05 | 2025-06-26
| 20 | Provision of Air Mobility services (logistics, personnel and MEDEVAC) | AUC/PAPS/CMD/NC/003 | NC | RFQ/DIR | DC | 9100000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29 | 2025-06-05 | 2025-06-26
| 21 | Sensitization training on the draft MNJTF SOP on recovered SALW | AUC/PAPS/CMD/NC/004 | NC | RFQ | LC | 50000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29 | 2025-06-05 | 2025-06-26
| 22 | Provision of Command, Control, Communication and Information (C3IS) Service for MNJTF including off-grid power source | AUC/PAPS/CMD/NC/005 | NC | RFQ | DC | 2800000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 23 | Provision of Level III Medical Services for MNJTF troops at Hospital de la Renaissance | AUC/PAPS/CMD/NC/006 | NC | RFQ/DIR | DC | 500000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-04-17 | 2025-04-24
| 24 | Provision of Level III medical services for MNJTF troops at Maiduguri | AUC/PAPS/CMD/NC/007 | NC | RFB | LC | 500000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29 | 2025-06-05 | 2025-06-26
| 25 | JFA PAPS audit for period 2025 | AUC/PAPS/CMD/NC/008 | NC | RFB | LC | 20000 | JFA PAPS (100%) | 2025-03-02 | 2025-03-07 | 2025-03-14 | 2025-04-04 | 2025-04-11 | 2025-05-02 | 2025-05-09 | 2025-05-30 | 2025-06-06 | 2025-06-27
| 26 | ERM III audit (2 per year) | AUC/PAPS/CMD/NC/009 | NC | RFB | LC | 40000 | EU ERM III (100%) | 2025-03-03 | 2025-03-08 | 2025-03-15 | 2025-04-05 | 2025-04-12 | 2025-05-03 | 2025-05-10 | 2025-05-31 | 2025-06-07 | 2025-06-28
| 27 | JFA PAPS Audit framework | AUC/PAPS/CMD/NC/010 | NC | RFB | LC | 40000 | JFA PAPS (100%) | 2025-03-04 | 2025-03-09 | 2025-03-16 | 2025-04-06 | 2025-04-13 | 2025-05-04 | 2025-05-11 | 2025-06-01 | 2025-06-08 | 2025-06-29
| 28 | Coordinate regional efforts to address internal and transnational challenges in the SADC and COMESA (Working visit to COMESA to continue enhancing coordination and collaboration) | AUC/PAPS/CMD/NC/011 | NC | RFB | LC | 35080 | EU APSA IV (100%) | 2025-03-06 | 2025-03-11 | 2025-03-18 | 2025-04-08 | 2025-04-15 | 2025-05-06 | 2025-05-13 | 2025-06-03 | 2025-06-10 | 2025-07-01
| 29 | Hold AGA-REC joint initiative on Citizens engagement in Democratic Governance Processes | AUC/PAPS/CMD/NC/012 | NC | RFB | LC | 20000 | EU APSA IV (100%) | 2025-03-12 | 2025-03-17 | 2025-03-24 | 2025-04-14 | 2025-04-21 | 2025-05-12 | 2025-05-19 | 2025-06-09 | 2025-06-16 | 2025-07-07
| 30 | Support the implementation of the work plan of the PRC Sub Committee on HRDG | AUC/PAPS/CMD/NC/013 | NC | RFB | LC | 25000 | EU APSA IV (100%) | 2025-03-13 | 2025-03-18 | 2025-03-25 | 2025-04-15 | 2025-04-22 | 2025-05-13 | 2025-05-20 | 2025-06-10 | 2025-06-17 | 2025-07-08
| 31 | Mainstream Child Protection in Continental and Regional Early Warning Systems | AUC/PAPS/CMD/NC/014 | NC | RFB | LC | 53800 | EU APSA IV (100%) | 2025-03-15 | 2025-03-20 | 2025-03-27 | 2025-04-17 | 2025-04-24 | 2025-05-15 | 2025-05-22 | 2025-06-12 | 2025-06-19 | 2025-06-26
| 32 | Effectively pay for text messaging, software maintenance fees, upgrading of IT tools and accessories as well as payment for Bandwidth | AUC/PAPS/CMD/NC/015 | NC | RFB | LC | 60000 | EU APSA IV (100%) | 2025-03-16 | 2025-03-21 | 2025-03-28 | 2025-04-18 | 2025-04-25 | 2025-05-16 | 2025-05-23 | 2025-06-13 | 2025-06-20 | 2025-07-11
| 33 | Conduct annual Structural Vulnerability Assessment using the Africa Prospects tool | AUC/PAPS/CMD/NC/016 | NC | RFB | LC | 35010 | EU APSA IV (100%) | 2025-03-17 | 2025-03-22 | 2025-03-29 | 2025-04-19 | 2025-04-26 | 2025-05-17 | 2025-05-24 | 2025-06-14 | 2025-06-21 | 2025-07-12
| 34 | Finalize the Documentary on the EU APSA IV Programme | AUC/PAPS/CMD/NC/017 | NC | RFB | LC | 30000 | EU APSA IV (100%) | 2025-03-21 | 2025-03-26 | 2025-04-02 | 2025-04-23 | 2025-04-30 | 2025-05-21 | 2025-05-28 | 2025-06-18 | 2025-06-25 | 2025-07-16
| 35 | Conduct and Support Statutory Meetings on YPS (including Ministerial & Continental meetings) | AUC/PAPS/CMD/NC/018 | NC | RFB | LC | 38000 | EU APSA IV (100%) | 2025-03-22 | 2025-03-27 | 2025-04-03 | 2025-04-24 | 2025-05-01 | 2025-05-22 | 2025-05-29 | 2025-06-19 | 2025-06-26 | 2025-07-17
| 36 | Support Development and Adoption of National Action Plans (NAPs) on YPS, including Consultations with RECs/RMs and Member States | AUC/PAPS/CMD/NC/019 | NC | RFB | LC | 40000 | EU APSA IV (100%) | 2025-03-23 | 2025-03-28 | 2025-04-04 | 2025-04-25 | 2025-05-02 | 2025-05-23 | 2025-05-30 | 2025-06-20 | 2025-06-27 | 2025-07-18
| 37 | Support the Implementation of Youth-led Conflict Prevention Initiatives (including peace caravans, combating hate speech & genocidal ideologies, PCVE, preventing GBV, mitigating local and natural based conflicts etc.) | AUC/PAPS/CMD/NC/020 | NC | RFB | LC | 69000 | EU APSA IV (100%) | 2025-03-24 | 2025-03-29 | 2025-04-05 | 2025-04-26 | 2025-05-03 | 2025-05-24 | 2025-05-31 | 2025-06-21 | 2025-06-28 | 2025-07-05
| 38 | Support Regional Economic Communities/Regional Mechanisms (NARC, UMA) in the North Africa Region in Establishing Umbrella Civil Society Organizations (CSOs) for the Purpose of data collection and analysis from the field through Africa Reporter, in collaboration with the Economic, Social, and Cultural Council (ECOSOCC) and AU CEWS/Situation Room | AUC/PAPS/CMD/NC/021 | NC | RFB | LC | 65295 | EU APSA IV (100%) | 2025-03-26 | 2025-03-31 | 2025-04-07 | 2025-04-28 | 2025-05-05 | 2025-05-26 | 2025-06-02 | 2025-06-23 | 2025-06-30 | 2025-07-07
| 39 | Convene joint round table engagements between AU, IGAD, EAC and ICGLR including CSOs, academic, Think Tanks, on evolving political, security and humanitarian situation in the region with the aims of facilitating a coordinated approach to revolving them | AUC/PAPS/CMD/NC/022 | NC | RFB | LC | 26321 | EU APSA IV (100%) | 2025-03-27 | 2025-04-01 | 2025-04-08 | 2025-04-29 | 2025-05-06 | 2025-05-27 | 2025-06-03 | 2025-06-24 | 2025-07-01 | 2025-07-22
| 40 | Conduct trainings for the implementing partners on the M&E system of the Governance, Peace and Security Programme | AUC/PAPS/CMD/NC/023 | NC | RFB | LC | 26094 | EU APSA IV (100%) | 2025-03-28 | 2025-04-02 | 2025-04-09 | 2025-04-30 | 2025-05-07 | 2025-05-28 | 2025-06-04 | 2025-06-25 | 2025-07-02 | 2025-07-09
| 41 | Enhancement of knowledge Management for PSOD, ASF and AU PSOs | AUC/PAPS/CMD/NC/024 | NC | RFB | LC | 72000 | EU APSA IV (100%) | 2025-03-29 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29 | 2025-06-05 | 2025-06-26 | 2025-07-03 | 2025-07-24
| 42 | NARC, CEN-SAD, CAERT and academia on security challenges, threats and trends, experience sharing in North Africa region in view of joint planning activities and implementation of the PSC decisions. | AUC/PAPS/CMD/NC/025 | NC | RFB | LC | 33420 | EU APSA IV (100%) | 2025-03-31 | 2025-04-05 | 2025-04-12 | 2025-05-03 | 2025-05-10 | 2025-05-31 | 2025-06-07 | 2025-06-28 | 2025-07-05 | 2025-07-12
| 43 | develop a strategic framework to highlight AU PAPS key priorities for Central Africa Region | AUC/PAPS/CMD/NC/026 | NC | RFB | LC | 48144 | EU APSA IV (100%) | 2025-04-01 | 2025-04-06 | 2025-04-13 | 2025-05-04 | 2025-05-11 | 2025-06-01 | 2025-06-08 | 2025-06-29 | 2025-07-06 | 2025-07-27
| 44 | Support/Establish the creation of CSOs’ platforms, public participation, and civic engagements for peace, security, and development in Southern African countries. | AUC/PAPS/CMD/NC/027 | NC | RFB | LC | 77000 | EU APSA IV (100%) | 2025-04-02 | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-06-30 | 2025-07-07 | 2025-07-28
| 45 | Convene consultative working sessions between the AU, COMESA, SADC, and Southern Africa CSOs to improve cooperation, coherence, and complementarity while sharing best practices for interventions for peace, security, and development in Southern African countries, in line with EU APSA IV Steering Committee meeting outcome. | AUC/PAPS/CMD/NC/028 | NC | RFB | LC | 62550 | EU APSA IV (100%) | 2025-04-03 | 2025-04-08 | 2025-04-15 | 2025-05-06 | 2025-05-13 | 2025-06-03 | 2025-06-10 | 2025-07-01 | 2025-07-08 | 2025-07-15
| 46 | Support the implementation of joint flagship and transversal initiatives on AGA (governance, peace and security) as enablers to achieve Agenda 2063 (Aspiration 3,4,6) | AUC/PAPS/CMD/NC/029 | NC | RFB | LC | 30000 | EU APSA IV (100%) | 2025-04-04 | 2025-04-09 | 2025-04-16 | 2025-05-07 | 2025-05-14 | 2025-06-04 | 2025-06-11 | 2025-07-02 | 2025-07-09 | 2025-07-30
| 47 | Organize Statutory Steering Committee meetings on the Governance, Peace and Security Programme | AUC/PAPS/CMD/NC/030 | NC | RFB | LC | 485172 | EU APSA IV (100%) | 2025-04-05 | 2025-04-10 | 2025-04-17 | 2025-05-08 | 2025-05-15 | 2025-06-05 | 2025-06-12 | 2025-07-03 | 2025-07-10 | 2025-07-17
| 48 | Review Meetings with implementing partners (AU, RECs/RMs, AU organs/institutions)of the Governance, Peace and Security Programme | AUC/PAPS/CMD/NC/031 | NC | RFB | LC | 82216 | EU APSA IV (100%) | 2025-04-06 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06 | 2025-06-13 | 2025-07-04 | 2025-07-11 | 2025-07-18
| 49 | annual Technical Meeting jointly with the RECs/RMs, in line with the decision of the 4th APSA steering committee meeting | AUC/PAPS/CMD/NC/032 | NC | RFB | LC | 100136 | EU APSA IV (100%) | 2025-04-08 | 2025-04-13 | 2025-04-20 | 2025-05-11 | 2025-05-18 | 2025-06-08 | 2025-06-15 | 2025-07-06 | 2025-07-13 | 2025-08-03
| 50 | Supporting the establishment or strengthening of EWS of RECs/RMs | AUC/PAPS/CMD/NC/033 | NC | RFB | LC | 29580 | EU APSA IV (100%) | 2025-04-09 | 2025-04-14 | 2025-04-21 | 2025-05-12 | 2025-05-19 | 2025-06-09 | 2025-06-16 | 2025-07-07 | 2025-07-14 | 2025-08-04
| 51 | Holding engagement between AU and RECs/RMs to enhance Indicators on different thematic areas | AUC/PAPS/CMD/NC/034 | NC | RFB | LC | 38575 | EU APSA IV (100%) | 2025-04-10 | 2025-04-15 | 2025-04-22 | 2025-05-13 | 2025-05-20 | 2025-06-10 | 2025-06-17 | 2025-07-08 | 2025-07-15 | 2025-08-05
| 52 | AU Field Missions and Liaison offices and CSOs through ECCOSOC on data collection (Africa Reporter) | AUC/PAPS/CMD/NC/035 | NC | RFB | LC | 39850 | EU APSA IV (100%) | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-05-14 | 2025-05-21 | 2025-06-11 | 2025-06-18 | 2025-07-09 | 2025-07-16 | 2025-07-23
| 53 | conducting conflict prevention missions to Member States, including support to election Situation Rooms | AUC/PAPS/CMD/NC/036 | NC | RFB | LC | 21120 | EU APSA IV (100%) | 2025-04-12 | 2025-04-17 | 2025-04-24 | 2025-05-15 | 2025-05-22 | 2025-06-12 | 2025-06-19 | 2025-07-10 | 2025-07-17 | 2025-07-24
| 54 | Pay subscription fee for online news sources (Reuters, BBC Monitoring, AFP, and New analytics as well as DSTV etc) | AUC/PAPS/CMD/NC/037 | NC | RFB | LC | 145000 | EU APSA IV (100%) | 2025-04-13 | 2025-04-18 | 2025-04-25 | 2025-05-16 | 2025-05-23 | 2025-06-13 | 2025-06-20 | 2025-07-11 | 2025-07-18 | 2025-07-25
| 55 | Support AU MS in the Prevention of Terrorism and Violent Extremism | AUC/PAPS/CMD/NC/038 | NC | RFB | LC | 28080 | EU APSA IV (100%) | 2025-04-14 | 2025-04-19 | 2025-04-26 | 2025-05-17 | 2025-05-24 | 2025-06-14 | 2025-06-21 | 2025-07-12 | 2025-07-19 | 2025-08-09
| 56 | Transportation, Accomodation, Interpretaion Equipment and Conference room hire to Hold Bi-annual Senior Officials consultations between AU and the RECs/RMs (two per year in April/May and Oct/Nov of each year) to implement the annual programme of work agreed upon by the Chairperson and Chief Executives of the RECs/RMs | AUC/PAPS/CMD/NC/039 | NC | RFB | LC | 60800 | EU APSA IV (100%) | 2025-04-15 | 2025-04-20 | 2025-04-27 | 2025-05-18 | 2025-05-25 | 2025-06-15 | 2025-06-22 | 2025-07-13 | 2025-07-20 | 2025-08-10
| 57 | Supply and delivery of Petrol/Diesel, Oil and Lubricant (POL) for vehicles and generators | AUC/PAPS/CMD/NC/040 | NC | RFQ/DIR | DC | 1400000 | EU | 2025-04-16 | 2025-04-21 | 2025-04-28 | 2025-05-19 | 2025-05-26 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-02 | 2025-06-09
| 58 | Purchase and Installation of Office Equipment as well as LAN and WAN - Network switch, router, hardware firewall, bridge network, mounting equipment including subscription for the AU Post-conflict Reconstruction and Development, Cairo, Egypt | AUC/PAPS/PCRD/NC/001 | NC | RFQ | LC | 75000 | MS(100%) | 2025-04-14 | 2025-04-19 | 2025-04-26 | 2025-05-17 | 2025-05-24 | 2025-06-14 | 2025-06-21 | 2025-07-12 | 2025-07-19 | 2025-08-09
| 59 | Organize the Africa Think Thank Summit | AUC/PMRM/NC/001 | NC | RFP | OC | 276572 | WB | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29 | 2025-10-04 | 2025-10-09 | 2025-10-14
| 60 | Advertisement & Communication services for the call for applications | AUC/PMRM/NC/002 | NC | QCBS | LC | 50000 | WB | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03
| 61 | stakeholder engagement meetings | AUC/PMRM/NC/003 | NC | RFP | LC | 20000 | WB | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
| 62 | Steering Committee Meetings | AUC/PMRM/NC/004 | NC | RFP | OC | 50000 | WB | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
| 63 | Independent Evaluation Committee selection Meetings | AUC/PMRM/NC/005 | NC | RFP | OC | 50000 | WB | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06
| 64 | Conduct Follow-up meetings to support the implementation of the recommendations from the events | AUC/PMRM/NC/006 | NC | DIR | OC | 54000 | WB | 2025-11-20 | 2025-11-25 | 2025-11-30 | 2025-12-05 | 2025-12-10 | 2025-12-15 | 2025-12-20 | 2025-12-25 | 2025-12-30 | 2026-01-04
| 65 | Conduct a stakeholder engagement meeting | AUC/PMRM/NC/007 | NC | RFQ | LC | 357506 | WB | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03
| 66 | Participation in AU Partnership Summits | AUC/PMRM/NC/008 | NC | RFQ | LC | 20226 | MS | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
| 67 | Selection of a service provider for the design and production of an information document on the progress made in the implementation of the Africa-Korea Framework of Cooperation 2017-2021 | AUC/SEBE/NC/001 | NC | RFQ | LC | 50000 | MS(100%) | 2025-01-01 | 2025-01-06 | 2025-01-13 | 2025-02-03 | 2025-02-10 | 2025-03-03 | 2025-03-10 | 2025-03-31 | 2025-04-07 | 2025-04-28
| 68 | Procurement of comunication and Visibilty Materials for the blue economy | AUC/SEBE/NC/002 | NC | RFQ | LC | 25000 | JFA | 2025-04-14 | 2025-04-19 | 2025-04-26 | 2025-05-17 | 2025-05-24 | 2025-06-14 | 2025-06-21 | 2025-07-12 | 2025-07-19 | 2025-08-09
| 69 | Procurement of workshop venues for training of Parliamentarian in 4 RECs | AUC/SEBE/NC/003 | NC | RFQ | OC | 45000 | MEA III | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 70 | Procurement of visibility materials for the MEA III Project | AUC/SEBE/NC/004 | NC | RFB | OC | 25000 | MEA III | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 71 | Procurement of venues for ACP meeting | AUC/SEBE/NC/005 | NC | RFQ | OC | 30000 | MEA III | 2025-02-01 | 2025-02-06 | 2025-02-21 | 2025-03-14 | 2025-03-21 | 2025-04-11 | 2025-04-18 | 2025-05-09 | 2025-05-16 | 2025-06-06
| 72 | Establishment of Situation Rooms (equipment, design and installation) | AUC/SEBE/NC/006 | NC | FIRM | LC | 250000 | Denmark | 2025-01-15 | 2025-01-20 | 2025-01-27 | 2025-02-17 | 2025-02-24 | 2025-03-17 | 2025-03-24 | 2025-04-14 | 2025-04-21 | 2025-05-12
| 73 | Maintenance Agreement and Services for the Heavy-duty Printing Machineries with the Suppliers. | AUC/DCMP/NC/001 | NC | DIR | LC | 25000 | MS(100%) | 2025-04-04 | 2025-04-09 | 2025-04-16 | 2025-05-07 | 2025-05-14 | 2025-06-04 | 2025-06-11 | 2025-07-02 | 2025-07-09 | 2025-07-16
| 74 | Procure services (Conference Package (ticktets, Honorarium); video production; interpretation equipment/services; audio and lighting etc) for 5th STC-Youth Culture and Sports | AUC/WGYD/NC/001 | NC | RFP | LC | 45000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 75 | Procure services (Conference Package; Tickets, Honorarium for AU Youth Volunteer program - AUYVC; Young Professional Programs - YPP | AUC/WGYD/NC/002 | NC | OC | LC | 200000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 76 | Procure services (conference Package; ticket and Honorarium African Youth Day and Youth Engagement events | AUC/WGYD/NC/003 | NC | RFP/RFQ | LC | 100000 |  | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 77 | Procure services (conference Package; ticket and Honorarium - Policy Advocacy and MS Capacity Building and MS Technical Assistance activities | AUC/WGYD/NC/004 | NC | OC | LC | 210000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 78 | Procure services (Conference Package (ticktets, Honorarium), video production, for the WYFEI 2030 Cohort Southern Africa Bootcamp. | AUC/WGYD/NC/005 | NC | RFP/QCBS | OC | 60000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 79 | Procure services ( Ticket, Honorarium..) for WYFEI at the IATF2025 | AUC/WGYD/NC/006 | NC | RFQ | OC | 20000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 80 | Procure services (conference package, tickets, honorarium, interpretation - support to GIMAC, AWLN, PAWO, GEWE Multistakeholder platforms) | AUC/WGYD/NC/007 | NC | OC | OC | 235000 | WB EAGER | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 81 | Operationalize the mainstreaming of AU Gender and Youth implementation including advocacy missions (procure services, Conference Package (ticktets, Honorarium) | AUC/WGYD/NC/008 | NC | RFP | OC | 20675 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 82 | Procure services, conference package, interpretation equipments/service 10th STC GEWE | AUC/WGYD/NC/009 | NC | RFQ | OC | 38000 | MS(100%) | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
| 83 | Selection of service providers for the Budget Retreat of the PRC Sub-Committee on GSCBFAM and F15 Experts | AUC/FIN/NC/001 | NC | RFQ | OC | 294580 | MS(100%) | 2024-04-10 | 2024-04-15 | 2024-04-22 | 2024-05-13 | 2024-05-20 | 2024-06-10 | 2024-06-17 | 2024-07-08 | 2024-07-15 | 2024-08-05
| 84 | Selection of service providers for Strengthen Public Financial management | AUC/FIN/NC/002 | NC | RFQ | LC | 160200 | JFA(100%) | 2024-06-14 | 2024-06-19 | 2024-06-26 | 2024-07-17 | 2024-07-24 | 2024-08-14 | 2024-08-21 | 2024-09-11 | 2024-09-18 | 2024-10-09
| 85 | Selection of service providers for AU Budget Manual and Accounting Procedures | AUC/FIN/NC/003 | NC | RFQ | LC | 50000 | JFA(100%) | 2024-06-11 | 2024-06-16 | 2024-06-23 | 2024-07-14 | 2024-07-21 | 2024-08-11 | 2024-08-18 | 2024-09-08 | 2024-09-15 | 2024-10-06
| 86 | Selection of service providers Strengthen Internal controls and Business proceses for efficiency and effectiveness | AUC/FIN/NC/004 | NC | RFQ | LC | 63040 | WB | 2024-07-05 | 2024-07-10 | 2024-07-17 | 2024-08-07 | 2024-08-14 | 2024-09-04 | 2024-09-11 | 2024-10-02 | 2024-10-09 | 2024-10-30
| 87 | Payment of fee for Maintenance and hosting of AU Learn management System for a revamped training curriculum perfromance management and deploy trainings | AUC/HRM/NC/001 | NC | DIR | DC | 30000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-07-27 | 2025-08-17 | 2025-08-24 | 2025-09-14 | 2025-09-21 | 2025-10-12 | 2025-10-19 | 2025-11-09
| 88 | Payment of hosting of AU Academy Online Platform to revamp training curriculum on performance management and deploy trainings - AU Academy | AUC/HRM/NC/002 | NC | RFQ | LC | 30000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-07-27 | 2025-08-17 | 2025-08-24 | 2025-09-14 | 2025-09-21 | 2025-10-12 | 2025-10-19 | 2025-11-09
| 89 | Purchase of off the shelve online courses for the AU Academy to revamp training curriculum on performance management and deploy trainings | AUC/HRM/NC/003 | NC | RFQ | LC | 30000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-07-27 | 2025-08-17 | 2025-08-24 | 2025-09-14 | 2025-09-21 | 2025-10-12 | 2025-10-19 | 2025-11-09
| 90 | Procure Stationary items - For the delivery of Spanish Courses | AUC/HRM/NC/004 | NC | RFQ | LC | 30000 | WB - Biashara | 2025-07-15 | 2025-07-20 | 2025-07-27 | 2025-08-17 | 2025-08-24 | 2025-09-14 | 2025-09-21 | 2025-10-12 | 2025-10-19 | 2025-11-09
| 91 | Provision of Comprehensive Medical Insurance and Employee Assistance Programme (EAP) for AU Staff and Eligible Dependents – Global Coverage | AUC/HRM/NC/005 | NC | RFP | OC | 1000000 | MS(80%) IPs(20%) | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-09-10 | 2025-09-17 | N/A | N/A | N/A | 2025-09-24 | 2025-10-01
| 92 | Provision of Comprehensive Travel Insurance for AU Staff and Clients on Official Travel | AUC/HRM/NC/006 | NC | RFP | OC | 100000 | MS(80%) IPs(20%) | 2025-09-01 | 2025-09-06 | 2025-09-13 | 2025-10-04 | 2025-10-11 | N/A | N/A | N/A | 2025-10-18 | 2025-10-25
| 93 | Provision of Group Life Insurance Coverage for AU Staff | AUC/HRM/NC/007 | NC | RFP | OC | 2750000 | MS(80%) IPs(20%) | 2025-09-01 | 2025-09-06 | 2025-09-13 | 2025-10-04 | 2025-10-11 | N/A | N/A | N/A | 2025-10-18 | 2025-10-25
| 94 | Designing and provision of goods for promotions: Diaries, Pens, Caps, T-shirts,Bags, Mugs, Cups, Banners etcs | AUC/HRM/NC/008 | NC | RFQ | OC | 50000 | WB, EU, JFA | 2025-09-15 | 2025-09-20 | 2025-09-27 | 2025-10-18 | 2025-10-25 | N/A | N/A | N/A | 2025-11-01 | 2025-11-08
| 95 | Catering services for Summit meetings (PRC, Executive Council, Assembly) and Retreats | AUC/OSC/NC/001 | NC | RFQ | LC | 250000 | MS | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-07
| 96 | Temporary recruitment for Summit related activities (PRC, Executive Council, Assembly) | AUC/OSC/NC/002 | NC | RFQ | DC | 40000 | MS | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10
| 97 | Accommodation / tickets for Summit meetings (PRC, Executive Council, Assembly) and Retreats | AUC/OSC/NC/003 | NC | RFQ | LC | 500000 | MS | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10
| 98 | Press / media / security equipment for Summit meetings (PRC, Executive Council, Assembly) and Retreats | AUC/OSC/NC/004 | NC | RFQ | LC | 45000 | MS | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10
| 99 | Deployment of Human Rights Observers to countries experiencing or emerging out of conflicts | AUC//PAPS/GCPD/NC/001 | NC | RFQ | LC | 60000 | MS (100%) | 2025-04-11 | 2025-04-16 | 2025-04-23 | 2025-05-14 | 2025-05-21 | 2025-05-23 | 2025-05-25 | 2025-05-27 | 2025-05-28 | 2025-06-04
| 100 | Purchase and Installation of Office Equipment as well as LAN and WAN - Network switch, router, hardware firewall, bridge network, mounting equipment including subscription for the AU Post-conflict Reconstruction and Development, Cairo, Egypt | AUC//PAPS/GCPD/NC/002 | NC | RFQ | LC | 150000 | MS (100%) | 2025-04-14 | 2025-04-19 | 2025-04-26 | 2025-05-17 | 2025-05-24 | 2025-05-26 | 2025-05-28 | 2025-05-30 | 2025-05-31 | 2025-06-07
| 101 | Implementation of QIPs and PSPs in Liberia, CAR, Ethiopia and other relevant regional contexts | AUC//PAPS/GCPD/NC/003 | NC | RFQ | LC | 75000 | JFA (100%) | 2025-07-14 | 2025-07-19 | 2025-07-26 | 2025-08-16 | 2025-08-23 | 2025-08-25 | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-09-06
| 102 | Implementation of QIPs and PSPs in Burundi, E-DRC, Mozambique and other relevant regional contexts | AUC//PAPS/GCPD/NC/004 | NC | RFQ | LC | 75000 | JFA (100%) | 2025-08-14 | 2025-08-19 | 2025-08-26 | 2025-09-16 | 2025-09-23 | 2025-09-25 | 2025-09-27 | 2025-09-29 | 2025-09-30 | 2025-10-07
| 103 | Annual Popoola Management for Use of Electronic Tablets to Collect data during African Union Election Observation Missions | AUC//PAPS/GCPD/NC/005 | NC | RFQ | LC | 50000 | JFA (100%) | 2025-05-14 | 2025-05-20 | 2025-05-28 | 2025-06-03 | 2025-06-10 | 2025-06-12 | 2025-06-14 | 2025-06-16 | 2025-06-17 | 2025-06-24
| 104 | Participation in Meetings of the Law of the Sea and Maritime Matters | AUC/OLC/NC/001 | NC | RFQ | LC | 31020 | MS | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16
| 105 | Hearings before international courts and tribunals; defense in support of interests of the Union and its Member States | AUC/OLC/NC/002 | NC | RFQ | LC | 79316 | MS | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18
| 106 | Support African Group Legal Experts and defense of African interest and common position | AUC/OLC/NC/003 | NC | RFQ | LC | 21450 | MS | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03
| 107 | Legal Associates Program: On-boarding, salaries, allowances, separation entitlement | AUC/OLC/NC/004 | NC | RFQ | LC | 60000 | MS | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
| 108 | Meeting of Experts on Challenges of ratification/accession of OAU/AU treaties (EX.CL/847(XXV) Rev.1 | AUC/OLC/NC/005 | NC | RFQ | LC | 21775 | MS | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14
| 109 | Hire vehicle service providers | AUC/AFMD/TPT/NC/001 | NC | RFB | OC | TBA | CHARGEABLE TO RESPECTIVE BUDGET CODES | 2025-06-20 | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04
|  | Grand Total |  |  |  |  | 27627309
#REF!
Formulas:
Invitation Date = [Request Submission Date]+5
Evaluation Date = [Opening Date]+5
Opening of Financial Proposal = [Approval Date]+5

## Goods
GOODS
S/N | DESCRIPTION | REFERENCE NUMBER | CATEGORY SOURCING | SOURCING METHOD | TYPE OF COMPETITION | ESTIMATED AMOUNT IN USD | FINANCED BY | REQUEST SUBMISSION DATE | INVITATION DATE | OPENING DATE | EVALUATION DATE | APPROVAL DATE | OPENING OF FINANCIAL PROPOSAL | COMBINED EVALUATION | APPROVAL DATE | CONTRACT VETTING | CONTRACT SIGNING
1 | Procurement of IT Equipment to Support to Member states to operationalize the pillars in 4 Lighthouse Countries (LHCs). 8 computers and related accessories and software | AUC/ARD/GO/001 | GO | RFB | OC | 24000 | BMGF (100%) | 2025-01-01 | 2025-01-06 | 2025-02-05 | 2025-02-26 | 2025-03-05 | 2025-03-26 | 2025-04-02 | 2025-04-23 | 2025-04-30 | 2025-05-21
2 | Purchase of fisheries and aquaculture equipment (cage culture equipment, laboratory equipment and similar equipment) to enhance capacities of Aquatic Centres of Excellence | AUC/ARD/GO/002 | GO | RFB | OC | 100000 | SIDA (100%) | 2025-01-02 | 2025-01-07 | 2025-02-06 | 2025-02-27 | 2025-03-06 | 2025-03-27 | 2025-04-03 | 2025-04-24 | 2025-05-01 | 2025-05-22
3 | Procurements of Vehicle | AUC/ARD/GO/003 | GO | RFB | OC | 35000 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-03-08 | 2025-03-29 | 2025-04-05 | 2025-04-26 | 2025-05-03 | 2025-05-24 | 2025-05-31 | 2025-06-21
4 | Procure Branding and Promotional materials (publications, banners, Roll-ups etc) | AUC/ESTI/AfSA/GO/001 | GO | RFQ | OC | 50000 | EU(100%) | 2025-05-01 | 2025-05-06 | 2025-05-11 | 2025-05-16 | 2025-05-21 | 2025-05-26 | 2025-05-31 | 2025-06-05 | 2025-06-10 | 2025-06-15
5 | Procure Office Equipment (Chairs; Printers; Peripheral devices; paper shredder; specialised laptops/computers for image processing; Internet modems, software etc) | AUC/ESTI/AfSA/GO/002 | GO | RFQ | OC | 50000 | EU(100%) | 2025-03-30 | 2025-04-04 | 2025-05-04 | 2025-05-25 | 2025-06-01 | 2025-06-22 | 2025-06-29 | 2025-07-20 | 2025-07-27 | 2025-08-17
6 | Printing of 300 copies of the Africa's Development Dynamics Report | AUC/ETTIM/GO/001 | GO | RFQ | LC | 20000 | MS (100%) | 2025-09-04 | 2025-09-09 | 2025-09-16 | 2025-10-07 | 2025-10-14 | 2025-11-04 | 2025-11-11 | 2025-12-02 | 2025-12-09 | 2025-12-30
7 | Printing of 300 copies of the African Integration and Development Review Report | AUC/ETTIM/GO/002 | GO | RFQ | LC | 20000 | EU(100%) | 2025-09-02 | 2025-09-07 | 2025-09-14 | 2025-10-05 | 2025-10-12 | 2025-11-02 | 2025-11-09 | 2025-11-30 | 2025-12-07 | 2025-12-28
8 | Procurement Vehicles (2) | AU/HHS/ACSRM/GO/001 | GO | FBS | OC | 130000 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-03-08 | 2025-03-29 | 2025-04-05 | 2025-04-26 | 2025-05-03 | 2025-05-24 | 2025-05-31 | 2025-06-21
9 | New Furniture for the Centre | AU/HHS/ACSRM/GO/002 | GO | RFQ | LC | 50000 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-02-13 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29
10 | Generator | AU/HHS/ACSRM/GO/003 | GO | RFQ | LC | 50000 | MS(100%) | 2025-02-01 | 2025-02-06 | 2025-02-13 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-05-01 | 2025-05-08 | 2025-05-29
11 | Procurement of Office Equipment (10 Laptops for the COC, Printers, Scanners and furniture, Stationary and Office Supplies. | AU/HHS/COC/GO/001 | GO | RFQ | LC | 71500 | MS(100%) | 2025-08-29 | 2025-09-03 | 2025-09-10 | 2025-10-01 | 2025-10-08 | N/A | N/A | N/A | 2025-10-15 | 2025-10-22
12 | Procurement, installation and maintenance of Medical equipment | AUC/MHSD/GO/001 | GO | RFQ | OC | 130000 | MS(100%) | 2025-02-25 | 2025-03-02 | 2025-03-07 | 2025-03-12 | 2025-03-17 | 2025-03-22 | 2025-03-27 | 2025-04-01 | 2025-04-06 | 2025-04-11
13 | Purchase of furniture and fixture for Baby care centre | AUC/MHSD/GO/002 | GO | RFQ | OC | 22925.77 | MS(100%) | 2025-02-25 | 2025-03-02 | 2025-03-07 | 2025-03-12 | 2025-03-17 | 2025-03-22 | 2025-03-27 | 2025-04-01 | 2025-04-06 | 2025-04-11
14 | Purchase of Medicine and medical products and others. | AUC/MHSD/GO/003 | GO | RFQ | OC | 724652 | MS(100%) | 2025-02-25 | 2025-03-02 | 2025-03-07 | 2025-03-12 | 2025-03-17 | 2025-03-22 | 2025-03-27 | 2025-04-01 | 2025-04-06 | 2025-04-11
15 | Pruchase of MRI | AUC/MHSD/GO/004 | GO | RFQ | OC | 50000 | MS(100%) | 2025-02-25 | 2025-03-02 | 2025-04-01 | 2025-04-06 | 2025-05-06 | 2025-05-11 | 2025-06-10 | 2025-06-15 | 2025-07-15 | 2025-07-20
16 | Procurement of stationery and office supplies | AUC/OSSD/GO/001 | GO | RFQ | OC | 121309.0854 | MS (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
17 | purchase of printing items | AUC/OSSD/GO/002 | GO | RFQ | OC | 67516.8929 | MS (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
18 | purchase of IT supplies and accessories | AUC/OSSD/GO/003 | GO | RFQ | OC | 45445.632 | MS (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
19 | Purchase of furniture and fixture | AUC/OSSD/GO/004 | GO | RFQ | OC | 40770 | MS (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
20 | Purchase of office equipment | AUC/OSSD/GO/005 | GO | RFQ | OC | 71750 | MS (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
21 | Procurement of Security Uniforms | AUC/OSSS/GO/001 | GO | RFQ | LC | 60840 | MS (100%) | 2025-01-19 | 2025-01-24 | 2025-01-29 | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-07
22 | Tiff for Njara (Qty expressed in sacs of 100kgs) | AUC/PAPS/PCRD/GO/001 | GO | RFQ | OC/LC | 125250 | JAPAN | 2025-06-04 | 2025-06-11 | 2025-06-16 | 2025-06-21 | 2025-06-26 | 2025-07-01 | 2025-07-06 | 2025-07-11 | 2025-07-16 | 2025-07-21
23 | Communication and Visibility(CVP) support to MNJTF | AUC/PAPS/CMD/GO/001 | GO | RFQ | LC | 50000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-11 | 2025-03-16 | 2025-03-21 | 2025-03-26 | 2025-03-31 | 2025-04-05 | 2025-04-10 | 2025-04-15
24 | Drugs, reagents, and basic medical equipment for HQ MNJTF | AUC/PAPS/CMD/GO/002 | GO | RFQ | OC | 200000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-11 | 2025-03-16 | 2025-03-21 | 2025-03-26 | 2025-03-31 | 2025-04-05 | 2025-04-10 | 2025-04-15
25 | Acquisition of Knowledge and Institutional Learing products (Publications, Photos, Barners, Posters etc) for the Conflict management Directorate. | AUC/PAPS/CMD/GO/003 | GO | RFB | LC | 90000 | PB-JFA02 | 2025-06-29 | 2025-07-04 | 2025-07-09 | 2025-07-14 | 2025-07-19 | 2025-07-24 | 2025-07-29 | 2025-08-03 | 2025-08-08 | 2025-08-13
26 | Implementation of streamlined PAPS Knowledge Management system and practices (Procurement and renewal of software acquision and maintenance fees, upgrading of IT tools and accessories). | AUC/PAPS/CMD/GO/004 | GO | RFB | OC | 143000 | PB-MST01 | 2025-07-30 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-19 | 2025-08-24 | 2025-08-29 | 2025-09-03 | 2025-09-08 | 2025-09-13
27 | Purchase 1 colour printer, 1 UPS - back-up, 3 in one printers-scanner, refill of the heavy duty printer- scanner for the AU Centre for PCRD | AUC/PAPS/PCRD/GO/002 | GO | RFQ | LC | 20000 | JFA-PAPS | 2025-04-27 | 2025-05-02 | 2025-05-07 | 2025-05-12 | 2025-05-17 | 2025-05-22 | 2025-05-27 | 2025-06-01 | 2025-06-06 | 2025-06-11
28 | Branding & printing of promotional materials: Diary and calendar, caps, t-shirts, bottles, umbrellas, mugs stationary, USB flash disk, letterhead, envelopes, writing pad, wire band notebook etc. for the AU Centre for PCRD | AUC/PAPS/PCRD/GO/003 | GO | RFQ | LC | 25000 | IP & MS | 2025-04-27 | 2025-05-02 | 2025-05-07 | 2025-05-12 | 2025-05-17 | 2025-05-22 | 2025-05-27 | 2025-06-01 | 2025-06-06 | 2025-06-11
29 | Purchase of one Mercedes and one Toyota Prado for logistics support services for the AU Centre for PCRD, | AUC/PAPS/PCRD/GO/004 | GO | CDS | LC | 100000 | MS | 2025-01-27 | 2025-02-01 | 2025-02-06 | 2025-02-11 | 2025-02-16 | 2025-02-21 | 2025-02-26 | 2025-03-03 | 2025-03-08 | 2025-03-13
30 | Purchase of office equipment and supplies including consummables for the AU Centre for PCRD | AUC/PAPS/PCRD/GO/005 | GO | RFQ | LC | 25000 | JFA-PAPS | 2025-04-27 | 2025-05-02 | 2025-05-07 | 2025-05-12 | 2025-05-17 | 2025-05-22 | 2025-05-27 | 2025-06-01 | 2025-06-06 | 2025-06-11
31 | Visibility and promotional materials to support popularization of DRM strategy | AUC/PMRM/GO/001 | GO | RFQ | LC | 50680 | China (100%) | 2025-04-12 | 2025-04-17 | 2025-04-22 | 2025-04-27 | 2025-05-02 | 2025-05-07 | 2025-05-12 | 2025-05-17 | 2025-05-22 | 2025-05-27
32 | Promotional material for Coordination of AU Partnership engagements held at the Headquarters | AUC/PRO/GO/001 | GO | RFQ | LC | 57988 | MS | 2025-06-25 | 2025-06-30 | 2025-07-05 | 2025-07-10 | 2025-07-15 | 2025-07-20 | 2025-07-25 | 2025-07-30 | 2025-08-04 | 2025-08-09
33 | Procure Furniture (10 Desk, 10 chair and two (02) executive tables) (GCCA+). | AUC/SEBE/GO/001 | GO | RFQ | LC | 20000 | EU (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
34 | Procurement of Promotional Materials for ECCAS and AUC GCCA+ | AUC/SEBE/GO/002 | GO | RFQ | LC | 50000 | EU (100%) | 2025-01-10 | 2025-01-15 | 2025-01-20 | 2025-01-25 | 2025-01-30 | 2025-02-04 | 2025-02-09 | 2025-02-14 | 2025-02-19 | 2025-02-24
35 | IT Equipment | AUC/SEBE/GO/003 | GO | RFQ | OC | 37000 | EU (100%) | 2025-03-06 | 2025-03-11 | 2025-03-16 | 2025-03-21 | 2025-03-26 | 2025-03-31 | 2025-04-05 | 2025-04-10 | 2025-04-15 | 2025-04-20
36 | Data server (ClimSA - ECCAS) | AUC/SEBE/GO/004 | GO | RFQ | OC | 48000 | EU (100%) | 2025-04-27 | 2025-05-02 | 2025-05-07 | 2025-05-12 | 2025-05-17 | 2025-05-22 | 2025-05-27 | 2025-06-01 | 2025-06-06 | 2025-06-11
37 | Automatic weather stations (AWS) - ClimSA | AUC/SEBE/GO/005 | GO | RFQ | OC | 100000 | EU (100%) | 2025-04-27 | 2025-05-02 | 2025-05-07 | 2025-05-12 | 2025-05-17 | 2025-05-22 | 2025-05-27 | 2025-06-01 | 2025-06-06 | 2025-06-11
38 | Confection Banners and visibility materials (bags, T shirt, Cup, Note Books)for DRR Unit | AUC/SEBE/GO/006 | GO | RFQ | OC | 50000 | EU/UNDP | 2025-01-01 | 2025-01-06 | 2025-01-11 | 2025-01-16 | 2025-01-21 | 2025-01-26 | 2025-01-31 | 2025-02-05 | 2025-02-10 | 2025-02-15
39 | Procurement of office supplies including 100 Rims of Papers, Cartridge | AUC/SEBE/GO/007 | GO | RFQ | LC | 40000 | EU/UNDP | 2025-01-08 | 2025-01-13 | 2025-01-20 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-02-24 | 2025-03-03
40 | Provide equipement ( computers, copying machine, printers to three national SSR coordination offices from Member States including Gambia, Madagascar and Mali | AUC/PAPS/GCPD/GO/001 | GO | RFQ | LC | 25000 | JFA- PAPS (100%) | 2025-04-27 | 2025-05-02 | 2025-05-27 | 2025-06-16 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31
41 | Enhance Data Center Capacity - PAM Licenses | AUC/MISD/GO/001 | GO | RFB | OC | 200000 | MS (100%) | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
42 | Upgrade and Modernize Network Infrastructure/Security | AUC/MISD/GO/002 | GO | RFB | OC | 2396880 | MS (100%) | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
43 | Procurement of IT Equipment and End user devices under IT replacement plan (desktops, All-in-one, Laptops and Printers solutions) | AUC/MISD/GO/003 | GO | RFB | OC | 668118 | MS (100%) | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
44 | Purchase of Heavy-duty banner maker | AUC/DCMP/GO/001 | GO | DIR | OC | 24000 | MS (100%) | 2025-03-04 | 2025-03-09 | 2025-03-14 | 2025-03-19 | 2025-03-24 | 2025-03-29 | 2025-04-03 | 2025-04-08 | 2025-04-13 | 2025-05-20
45 | Spare parts and accessories -Large size full-color Heidelberg Versafire EP digital press, Large size monochrome SEAP digital printing press, GUANGMING SWAFM-1050 large size laminating machine and Kodak Q800 CTP plate setter | AUC/DCMP/GO/002 | GO | DIR | OC | 21250 | MS(100%) | 2025-07-04 | 2025-07-09 | 2025-07-14 | 2025-07-19 | 2025-07-24 | 2025-07-29 | 2025-08-03 | 2025-08-08 | 2025-08-13 | 2025-09-19
46 | Procure Branding and Promotional materials (publications, banners, Roll-ups etc) | AUC/WGYD/GO/001 | GO | RFB | OC | 50000 | MS (100%) | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22
47 | Procurment of Computers and Office Equipment and Supplies | AUC/WGYD/GO/002 | GO | RFB | LC | 50000 | WB EAGER | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22
48 | Procure Branding and Promotional materials | AUC/WGYD/GO/003 | GO | RFQ | OC | 50000 | WB EAGER | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22
49 | Purchase a software to communicate survey results | AUC/HRM/GO/001 | GO | RFP | OC | 30000 | WB - Biashara | 2025-08-15 | 2025-08-20 | 2025-08-25 | 2025-08-30 | 2025-09-04 | 2025-09-09 | 2025-09-14 | 2025-09-19 | 2025-09-24 | 2025-09-29
50 | Promotional materials ( AUC Medical Insurance Tender & Welness Activities) | AUC/HRM/GO/002 | GO | RFQ | LC | 44400 | MS(80%) IP(20%) | 2025-10-01 | 2025-10-06 | 2025-10-13 | 2025-11-03 | 2025-11-10 | N/A | N/A | N/A | 2025-11-17 | 2025-11-24
51 | Printing machine consumables | AUC/OSC/GO/001 | GO | RFB | LC | 25000 | MS(100%) | 2025-01-01 | 2025-01-08 | 2025-01-13 | 2025-01-18 | 2025-01-23 | 2025-01-28 | 2025-02-02 | 2025-02-07 | 2025-02-12 | 2025-02-17
52 | Stationery items and IT tools/equipment for Summit meetings (PRC, Executive Council, Assembly) and Retreats | AUC/OSC/GO/002 | GO | RFQ | LC | 60000 | MS(100%) | 2025-01-01 | 2025-01-08 | 2025-01-13 | 2025-01-18 | 2025-01-23 | 2025-01-28 | 2025-02-02 | 2025-02-07 | 2025-02-12 | 2025-02-17
53 | Purchase of Ceremonial Items: flags, name plates,..etc | AUC/OSC/GO/003 | GO | RFQ | LC | 57988 | MS(100%) | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-04 | 2025-08-09 | 2025-08-14 | 2025-08-19
54 | Furniture for Buiding A | AUC/AFMD/GO/001 | GO | RFQ | LC | 250000 | AU Property Acquisition Fund | 2025-08-12 | 2025-08-17 | 2025-09-16 | 2025-10-07 | 2025-10-14 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16
55 | Upgrade of the Old Conference Center interpretation equipment, camera, Displays and others | AUC/AFMD/GO/002 | GO | RFB | OC | 200000 | MS(100%) | 2025-02-05 | 2025-02-10 | 2025-02-15 | 2025-02-20 | 2025-02-25 | 2025-03-02 | 2025-03-07 | 2025-03-12 | 2025-03-17 | 2025-03-22
56 | Purchase two vehicles for AIMEC office in Tunisia | AUC/AIMEC/GO/001 | GO | RFP | OC | 60000 | MS | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16
| Grand total |  |  |  |  | 7380263.3803

## Works
AFRICAN UNION ANNUAL PROCUREMENT PLAN AS OF AUGUST 2025
WORKS
| S/N | Description | Reference Number | Category Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
| 1 | Renovation of AU Old Compound Perimeter Fence, Gates, Retaining Walls, Old Compound Road and Drainage. | AUC/AFMD/W/001 | W | RFQ | OC | 100000 | MS (100%) | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-18 | 2025-02-23 | 2025-02-28 | 2025-03-05 | 2025-03-10 | 2025-03-15 | 2025-03-20
| 2 | Deployment Garbage Collection and Sorting Platform | AUC/AFMD/W/002 | W | RFB | OC | 250000 | MS(100%) | 2025-02-04 | 2025-02-09 | 2025-02-14 | 2025-02-19 | 2025-02-24 | 2025-03-01 | 2025-03-06 | 2025-03-11 | 2025-03-16 | 2025-03-21
| 3 | Africa House Renovation | AUC/AFMD/W/003 | W | RFB | LC | 2100000 | AU Property Acquisition Fund | 2025-08-28 | 2025-09-02 | 2025-10-02 | 2025-10-23 | 2025-10-30 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02
| 4 | Renovation of Building B | AUC/AFMD/W/004 | W | RFB | OC | 1982795 | AU Property Acquisition Fund | 2025-08-28 | 2025-09-02 | 2025-10-02 | 2025-10-23 | 2025-10-30 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02
| 5 | AUC Compound Fence Reinforcement | AUC/AFMD/W/005 | W | RFB | LC | 969500 | AU Property Acquisition Fund | 2025-08-18 | 2025-08-23 | 2025-09-22 | 2025-10-13 | 2025-10-20 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22
| 6 | Security Shutters Warehouse | AUC/AFMD/W/006 | W | RFQ | LC | 75000 | AU Property Acquisition Fund | 2025-08-28 | 2025-09-02 | 2025-09-17 | 2025-10-08 | 2025-10-15 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17
| 7 | Minor Renovation of OCC | AUC/AFMD/W/007 | W | RFB | OC | 250000 | AU Property Acquisition Fund | 2025-08-12 | 2025-08-17 | 2025-09-16 | 2025-10-07 | 2025-10-14 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16
| 8 | Renovation maintenance for telemedicine room | AUC/MHSD/W/001 | W | RFP | OC | 70000 | MS | 2025-02-10 | 2025-02-15 | 2025-02-20 | 2025-02-25 | 2025-03-02 | 2025-03-07 | 2025-03-12 | 2025-03-17 | 2025-03-22 | 2025-03-27
| 9 | Renovation maintenance for Baby care centre | AUC/MHSD/W/002 | W | RFP | OC | 30840 | SP | 2025-02-10 | 2025-02-15 | 2025-03-17 | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-06-30
| 10 | Renovation for Emergency Operation Centre | AUC/MHSD/W/003 | W | RFP | OC | 50000 | MS | 2025-02-10 | 2025-02-15 | 2025-03-17 | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-06-30
| 11 | Renovation of Health Promotion Unit | AUC/MHSD/W/004 | W | RFP | OC | 125000 | MS | 2025-02-10 | 2025-02-15 | 2025-03-17 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19
| 12 | Renovation for MRI Rooms | AUC/MHSD/W/005 | W | RFP | OC | 50000 | SP | 2025-02-10 | 2025-02-15 | 2025-03-17 | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-06-30
| 13 | Construction of full height sliding gate | AUC/OSSS/W/001 | W | RFB | OC | 97364 | MS (100%) | 2025-05-10 | 2025-05-15 | 2025-06-14 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16
| 14 | CIMIC projects for the Multinational Joint Task Force (MNJTF) against Boko Haram Sector 1. | AUC/PAPS/CMD/W/001 | W | RFQ | LC | 200000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-24 | 2025-05-15 | 2025-06-05 | 2025-06-26 | 2025-07-17 | 2025-08-07
| 15 | CIMIC projects for the Multinational Joint Task Force (MNJTF) against Boko Haram Sector 2. | AUC/PAPS/CMD/W/002 | W | RFQ | LC | 200000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15
| 16 | CIMIC projects for the Multinational Joint Task Force (MNJTF) against Boko Haram Sector 3. | AUC/PAPS/CMD/W/003 | W | RFQ | LC | 200000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15
| 17 | CIMIC projects for the Multinational Joint Task Force (MNJTF) against Boko Haram Sector 4. | AUC/PAPS/CMD/W/004 | W | RFQ | LC | 200000 | EU | 2025-03-01 | 2025-03-06 | 2025-03-13 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15
| 18 | Construction of the African Union Medical Training Center At the African Union Logistics Base in Doula, Cameroon | AUC/PAPS/CMD/W/005 | W | RFB | OC | 4200000 | MS (100%) | 2025-03-01 | 2025-03-06 | 2025-04-05 | 2025-04-26 | 2025-05-17 | 2025-06-07 | 2025-06-28 | 2025-07-19 | 2025-08-09 | 2025-08-30
| 19 | Construction of the AU Human Rights Memorial as per Assembly Decision | AUC/PAPS/GCPD/W/001 | W | RFP | LC | 200000 | MS (100%) | 2025-05-10 | 2025-05-17 | 2025-05-30 | 2025-06-15 | 2025-06-30 | 2025-07-03 | 2025-07-06 | 2025-07-09 | 2023-07-10 | 2023-07-17
|  | Grand Total |  |  |  |  | 11350499

## OVER ALL SUMMARY
2025 Annual procurement plan
No. | Category | Total Amount (USD)
2 | CONSULTANCY SERVICES | 37647785.46
1 | NON-CONSULTANCY SERVICES | 27627309
3 | WORKS | 11350499
4 | GOODS | 7380263.3803
TOTAL |  | 84005856.8403

## Sourcing Methods Mapping
Procurement Category Code | GO | CW | CS | NC | Sourcing Category Code | Sourcing Category Definition | Review Type | Type of Competition Code | Sourcing Type of Competition
GO | RFP | RFP | QCBS | RFP | GO | Goods | Post | OC | Open Competition
CW | RFB | RFB | FBS | RFB | W | Works | Prior | LC | Limited Competition
CS | RFQ | RFQ | LCS | RFQ | CS | Consultant Services |  | DC | Direct Competition
NC | DIR | DIR | QBS | DIR | NC | Non-Consulting Services
| UN | UN | CDS | UN
| EA | CDD | INDV | EA | Sourcing Method Code (CS) | Sourcing Method Definition |  | Sourcing Method Code (GO) | Sourcing Method Definition
| IMP | FCA | UN | CDD | QCBS | Quality and Cost-Based Selection |  | RFP | Request for Proposals
| COMM | APA | NPO | FCA | FBS | Fixed Budget Selection |  | RFB | Request for Bids
| CDD | PPP | BANK | APA | LCS | Least Cost Selection |  | RFQ | Request for Quotations
| APA | CP | PRA | PPP | QBS | Quality Based Selection |  | DIR | Direct Selection
| CP |  | CAPA | CP | CQS | Consultant Qualification Selection |  | UN | UN Agencies (Direct)
|  |  | CCP |  | CDS | Direct Selection
[5 empty] | INDV | Individual Consultant Selection
[5 empty] | UN | UN Agencies (Direct)
[5 empty] | PRA | Procurement Agents
[5 empty] | Sourcing Method Code (W) | Procurement Method Definition |  | Sourcing Method Code (NC) | Procurement Method Definition
[5 empty] | RFP | Request for Proposals |  | RFP | Request for Proposals
[5 empty] | RFB | Request for Bids |  | RFB | Request for Bids
[5 empty] | RFQ | Request for Quotations |  | RFQ | Request for Quotations
[5 empty] | DIR | Direct Selection |  | DIR | Direct Selection
[5 empty] | UN | UN Agencies (Direct) |  | UN | UN Agencies (Direct)
[5 empty] | FCA | Force Account |  | FCA | Force Account
[5 empty] | PPP | Public Private Partnerships |  | PPP | Public Private Partnerships